2nd CAPSTONE PROJECT STATUS CHECKING FORM

| Project Title: | CS-57 [AI / Software Engineering] Human-Al Data Annotation, Provenance, and Dataset Evaluation Platform |
| --- | --- |
| Project Client: | Hunter Xu |
| Group Number: | CS-57 |
| Date of client meeting: | 23-September-2026 |

| Status Highlight | Summary of report & feedback |
| --- | --- |
| Overall Project Status |  |
| Progress and Achievements | - Basic workflow works end to end - Invited into an organization → Admin & Task owner create project → create task → add items into task (done) - Annotators perform data annotation → Reviewers review, then accept/reject→ send item to dispute if conflicts happen between reviewers (in-progress) - Expert (Arbitrator) resolves the dispute — a basic ruling works; the client's revised version (accept, return or reject) is in progress → item finalised (done) - Admin & Task owner export reviewed and finalised items (done); the full provenance history with each exported item (to-do) - AI-Provider integration complete — typed provider interface with mock and live interchangeable, batch jobs, per-item job status, background worker, retry that separates transient from permanent failures - Trustworthy Foundations complete — legacy review mutations retired behind 410 Gone, cross-project and cross-org write protection, environment and seed-data repair - Annotation & Human Judgement — draft ownership, atomic draft submission, custom task and label definitions with schema upload - Organization management backend done (members, invitations, roles); project review-policy settings mostly done; task status changes (activate, pause, complete) in progress this sprint - Migrated to PostgreSQL 18 while keeping SQLite working — local development stays fast, CI tests the production engine, enabling concurrent data processing in multi-user and batch scenarios - 452 backend tests pass (4 skipped) and 205 frontend tests across 27 files on the main branch as of 23 September; every push runs the backend tests against both SQLite and PostgreSQL, with PostgreSQL set to a non-UTC timezone to catch date bugs - Governance rules enforced on the server, not only hidden in the UI — for example, only the author can edit their draft, users cannot write into another organisation's projects, reviewers cannot approve their own annotations, and a finalised item rejects further edits; the same self-approval check for disputed items is being added this sprint |
|  | Client’s feedback: |
| Key Issues |  |
| Obstacles & Risks | - Raised at the first checking — inherited defects: 30 defects were catalogued in the inherited code; 20 are fixed or have a fix merged, including 3 of the 6 critical ones. As the client directed, the rest are fixed when a feature being built depends on them, not in a separate clean-up phase. - Raised at the first checking — no review workflow: resolved. Every change now goes through a pull request reviewed by another team member (25 merged since 6 September), and automated tests run on every push; the one gap is GitHub branch protection, below. - Evaluation and provenance not started: there is no code yet for the evaluation harness (automated re-runs of the whole workflow), the casebook of 40–60 test cases, or the provenance log (a per-item record of who did what, when, and under which guideline). These are heavily weighted deliverables, with half the semester left. - Release depends on provenance: the release export planned for week 10 must list each item's history and refuse items whose history is incomplete, but the provenance log is currently scheduled for week 11. - Design questions settled with the client as work reaches them: some expected behaviours can only be confirmed once a feature is being built — for example, what happens after an expert rules on a dispute, who may reopen a finalised item, and how an uploaded dataset is split into items. Waiting for an answer can hold a user story, and an answer can reveal work that was not in the backlog; this week's answers added three new stories. This tests the team's agile planning: stories have to be re-scoped and the remaining weeks re-planned without losing momentum. |
|  | Client’s feedback: |
| Deviation from Timeline | - Against the plan presented at the first checking: user stories and the pull-request workflow (week 5) are done; the core annotation backend (weeks 7–8) is done apart from task status changes, in progress this week; review, roles and dispute work (weeks 9–10) started early and is in progress; the end-to-end run on the provided datasets (week 11) needs JSONL import, brought forward to this sprint. The separate schema and contract review (week 6) was replaced by fixing each mismatch inside the feature that needs it. - Scope since the first checking: the first checking agreed to deliver the core workflow first and treat further functionality as extension work, so provenance, releases and evaluation were not in that plan. The brief and the client's answers since then confirm they are required, so they are now scheduled from the mid-semester break to week 11. - Core platform: on track — the workflow works end to end up to review, while dispute handling, expert adjudication and export with provenance are incomplete; AI pre-annotation is complete apart from the batch progress screen (under review), and the PostgreSQL migration landed without stalling feature work - Evaluation and provenance: behind — both unstarted with the back half of semester remaining. This is a deviation in sequencing rather than total effort: the team front-loaded the platform and deferred the assessment-weighted deliverables. For evaluation the brief asked for the opposite ordering - Review and adjudication: in progress — draft ownership, the self-approval check, sending work back to the annotator and locking finalised items are merged; this sprint adds a work queue where annotators and reviewers pick up available items, an independent second review for a sample of items, and a separate record of each expert ruling. - A few week-7 items carried over into week 8 — the work-queue API, member-management screens, project-policy settings and the self-approval check for disputes; the other deviations are in work not yet started, not in work delivered late |
|  | Client’s feedback: |
| Next steps |  |
| Milestones | From the plan presented at the first checking - Week 5 User stories and the pull-request review workflow — Achieved - Week 6 Schema and contract validation — Replaced: mismatches are fixed inside each feature - Weeks 7–8 Core annotation backend (task setup, AI annotation, drafts) — Achieved, plus AI provider integration and the PostgreSQL migration; task status changes in progress - Weeks 9–10 Human review, role-based governance and dispute resolution — In progress, started early in week 7 - Week 11 End-to-end run on the provided datasets — In progress: JSONL import brought forward to week 8 - Week 12 Hardening, documentation and demo preparation — Planned - Week 13 Final presentation and report — Planned Added since the first checking (brief and client answers) - Mid-semester break Evaluation harness with repeatable runs and regression reporting — Not started - Weeks 10–11 Casebook of 40–60 adversarial and realistic cases — Not started; 40 cases by week 10 - Weeks 9–11 Provenance log, versioned sources and immutable releases with manifests — Not started; the provenance log is currently in week 11 and should move earlier |
|  | Client’s feedback: |
| How to address obstacles & risks mentioned above in the ‘Key Issues’ | - Evaluation first in the mid-semester break: the break is used to build the harness, and every bug found while scenario-testing becomes a new case; target 40 cases by week 10. - Provenance log before the release export: move the provenance log ahead of the week-10 release work, so the export reads real item history instead of having it added afterwards. - Decisions recorded as they arrive: each client decision is written up as an architecture decision record (a short note of the decision, the alternatives and the reasons), and the affected backlog items and tickets are updated the same day; further questions go to the client as GitHub issues. - Repository controls: every pull request runs the backend tests on both databases and, by team rule, is reviewed by someone other than its author; the server blocks write across projects, and blocking reads across projects follows after the core workflow, if time allows. |
|  | Client’s feedback: |

All group member signatures (either handwritten or digital signatures):

_______________________________________________________________________________________________

Client signatures (either handwritten or digital signatures):

_______________________________________________________________________________________________