## Start Here
CS-57 - Contribution Tracker
Human-AI Data Annotation, Provenance & Dataset Evaluation Platform ¦ Group CS-57 ¦ Client: Hunter Xu
The one rule
After your pull request is merged into main, add ONE row to the 'Contribution Log' tab. That is the whole process. Every other tab fills itself in from those rows.
What each tab is for
Contribution Log | The only tab you type into. One row per merged PR. Cream headers = you fill in; grey headers = filled in automatically, do not type in them.
Dashboard | Automatic. Who merged what, per week and in total; review health; the split across frontend / backend / AI.
Jira Board | Who owns which bundle, how much of the committed scope is done, workload per person, and every issue on the board matched to the story it serves. Fill in the nine Owner cells once; the rest is a snapshot of docs/Jira.csv plus live PR counts.
Client Report | Set a date range at the top and this becomes the numbers block for the Status Checking form and the weekly client meeting.
Lists | Reference data behind the dropdowns and the automatic columns. Only edit the Week 1 Monday date, and only once.
When you finish a story
Work through this before you ask for a review. If you cannot tick items 1 and 2, the story is not finished - which is fine, but log the PR with 'Story complete? = No'.
1. Open the story in user-stories.html and re-read its acceptance criteria - every numbered criterion, not the one you remember. This is what 'done' means for that story.
2. The checks pass: npm run typecheck and the test suite run clean in whatever you touched (story A2).
3. There is a test covering the behaviour you changed, not only the code you wrote.
4. Anything a teammate could not guess is written down - a change note, and a decision record if you chose between real alternatives.
5. Open the PR with the story ID in the title, e.g. 'C2 - task queue progress'.
6. Request review from someone who did not write the code (story A1), and move the SCRUM ticket to In Review.
7. Once it is merged: move the SCRUM ticket to Done, then add your row to the Contribution Log.
8. Set 'Story complete? = Yes' only if every acceptance criterion is now met. If it closed a catalogued defect, put the issue number in 'Defects closed'.
How to log a merged PR
1. Open 'Contribution Log' and go to the first empty row.
2. Date merged - the date the PR landed on main. The Week column fills itself in from this.
3. Member is you. Reviewed by is the teammate who approved the PR. They must be different people (story A1 - no change reaches main without a second person's review); the sheet turns the row red if they are not.
4. Story ID - pick the backlog story the work serves (A1 ... K4). The story title, epic and priority appear automatically.
5. What changed - one sentence a non-engineer can understand. This sentence is what gets read out to the client, so write it for the client, not for the team.
6. Story complete? - answer 'Yes' only when nothing further is needed for that story. This is what drives every progress number in the workbook.
What a good row looks like
| Date merged | Member | Reviewed by | Work type | Story ID | What changed (plain English, for the client) | Story complete?
| 2026-09-08 | Hanchen Wang | Michael Max | Feature | C2 | A task with 1,000 items now runs in the background and shows a live progress bar, instead of freezing the page. | No - more work to come
| 2026-09-09 | Yi Geng | Dishank Aswal | Defect fix | C3 | When the AI is unavailable the item is now marked 'AI failed' instead of being filled with an invented bounding box. | Yes - story complete
| 2026-09-10 | Parth | Tok Tin Chung | Client / PM / Report | K2 | Wrote up the Week 6 status report and the client's decision on dispute routing. | N/A - not story work
Note what the summaries do not say: no file names, no function names, no ticket jargon. Write the sentence the client would understand if it were read out loud.
Ground rules
- One row per merged PR - not per commit, and not per day of work.
- Log it the same day it merges. A log reconstructed from memory in Week 12 is worth very little to anyone, including you.
- Never delete or reorder someone else's row. If a row is wrong, correct that row.
- Do not insert, delete or reorder columns. The other tabs read this one by column position and will break.
- Work that is not a PR still counts - client meetings, the report, the proposal, research spikes. Log it with work type 'Client / PM / Report' or 'Spike / Research' and leave the PR number blank.
- If one PR serves two stories, log the row against the main story and name the second one in Notes.
Setting it up (once)
1. In Google Sheets: File > Import > Upload this file, and choose 'Replace spreadsheet'.
2. The 'Lists' tab cell B2 holds the Monday of teaching Week 1: 3 August 2026, so that W6 is the week of Monday 7 September 2026 and W13 is the last. The week calendar in Lists columns T-V shows every week - glance at it, and only change B2 if a week there disagrees with your semester calendar.
3. Check the eight names in Lists column A are how people want to be named, then Share with all eight as Editor.
4. On 'Jira Board', fill in the nine Owner cells under 'Who owns what'. The allocation document names the bundles but nobody to own them, so this is the one decision the workbook cannot make for you.
5. Worth doing: on Contribution Log use View > Freeze > 1 row, and turn on Tools > Notification settings > 'Any changes' so the leads see new entries without asking.

## Contribution Log
Date merged | Week | Member | Reviewed by | Review OK? | PR # | PR link | Work type | Area / repo | Story ID | Story title | Epic | Pri | SCRUM ticket | Defects closed | What changed (plain English, for the client) | Story complete? | Notes / evidence
2026-08-28 | W4 | Yi Geng | Yi Geng | SELF-REVIEW | 1 |  | Refactor | Other | [7 empty] | No - more work to come
2026-09-07 | W6 | Hanchen Wang | Jingwei Lin | OK | 2 |  | DevOps / CI | CI / tooling | A2 | I can trust that a fix in one place hasn't broken another | A | P0 | SCRUM-82 | 12,13,25,26 |  | Yes - story complete
2026-09-07 | W6 | Jingwei Lin | Hanchen Wang | OK | 4 |  | Feature | hej-api (backend) | G1 | My role determines what I can do | G | P0 | SCRUM-44 | 7 | Users now can only perform actions that the role allowed them to do. | Yes - story complete

## Dashboard
Dashboard
Everything here is calculated from the Contribution Log. Nothing on this tab needs to be typed.
PRS MERGED |  |  | STORIES TOUCHED |  |  | STORIES COMPLETE |  |  | SELF-REVIEWS
3 |  |  | 2 |  |  | 2 |  |  | 1
Contribution by member
Member | PRs merged | PRs reviewed | Features | Defect fixes | Tests / docs | Stories completed | First merge | Last merge | Share of PRs
Michael Max | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
Parth | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
Jingwei Lin | 1 | 1 | 1 | 0 | 0 | 1 | 2026-09-07 | 2026-09-07 | 33.33%
Hanchen Wang | 1 | 1 | 0 | 0 | 0 | 1 | 2026-09-07 | 2026-09-07 | 33.33%
Yi Geng | 1 | 1 | 0 | 0 | 0 | 0 | 2026-08-28 | 2026-08-28 | 33.33%
Dishank Aswal | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
Kanishka Kathait | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
Tok Tin Chung | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0%
TOTAL | 3 | 3 | 1 | 0 | 0 | 2
TOTAL counts distinct stories, so it can be lower than the column above if two people finished the same story.
PRs merged per week | [5 empty] | Weeks are calculated from the date merged. Blank weeks simply have nothing logged yet.
Week | Michael Max | Parth | Jingwei Lin | Hanchen Wang | Yi Geng | Dishank Aswal | Kanishka Kathait | Tok Tin Chung | Total
W1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W6 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2
W7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Where the work went | [5 empty] | Review health
Area / repo | PRs |  | Work type | PRs
hej-web (frontend) | 0 |  | Feature | 1 |  | PRs with a named reviewer | 2
hej-api (backend) | 1 |  | Defect fix | 0 |  | PRs reviewed by their own author | 1
packages/ui | 0 |  | Refactor | 1 |  | Rows with no reviewer recorded | 0
labeling_ai_assistnat_mvp (AI) | 0 |  | Tests | 0 |  | Rows with no story linked | 1
Database / schema | 0 |  | Documentation | 0 |  | Rows missing a plain-English summary | 2
CI / tooling | 1 |  | Spike / Research | 0
Docs / report | 0 |  | DevOps / CI | 1
Other | 1 |  | Client / PM / Report | 0

## Jira Board
Jira Board
The CS-57 board, matched to the 59 committed backlog stories. Status and assignees are a snapshot of docs/Jira.csv; PR counts are live from the Contribution Log. Only the nine Owner cells are typed.
WORK ITEMS |  | IN PROGRESS |  | IN REVIEW |  | DONE |  | IN SPRINT W6 |  | UNASSIGNED
73 |  | 17 |  | 1 |  | 1 |  | 21 |  | 55
Who owns what | [5 empty] | Fill in the nine Owner cells once. This is the only typing on this tab.
# | Work bundle | Owner | What it covers |  | Stories | To do | Doing | Done | PRs
1 | AI task queue | Parth | Task queue with progress bar; completed / failed / retry |  | 1 | 1 | 0 | 0 | 0
2 | AI provider & failures | Yi Geng | Annotation failure and the fake bounding-box fallback; integrate labeling_ai_assistnat_mvp |  | 1 | 0 | 1 | 0 | 0
3 | Project setup & status UI | Hanchen Wang | Project / policy / task update, dataset upload, status page |  | 7 | 6 | 1 | 0 | 0
4 | Task & item backend |  | Illegal item status, cross-project writes, non-transactional task registration, missing transition out of draft, task-item routes and services |  | 4 | 1 | 3 | 0 | 0
5 | Annotation page & judgement |  | Annotation page with judgement feedback or justification |  | 6 | 4 | 2 | 0 | 0
6 | Draft ownership & verdict |  | Finalised annotation overwrite, draft ownership, judgement verdict and feedback |  | 3 | 1 | 2 | 0 | 0
7 | Review, permissions & dispute |  | Reviewer correction, avoid self-review, review action, permission and dispute |  | 8 | 6 | 2 | 0 | 1
8 | Audit & history |  | Audit and history |  | 4 | 4 | 0 | 0 | 0
9 | Release & export |  | Release and export |  | 5 | 5 | 0 | 0 | 0
- | Unallocated |  | Not in the allocation document. Assign these before they become a surprise. |  | 20 | 9 | 4 | 1 | 1
Committed scope | [5 empty] | Done counts what the board says is done. A story with no ticket cannot be done. | By epic
Priority | Stories | Done | Doing | On board | % done |  | Epic | Stories | Done
P0 - committed core | 35 | 1 | 12 | 32 | 2.857% |  | A - Trustworthy Foundations | 5 | 1
P1 | 20 | 0 | 3 | 17 | 0% |  | B - Setting Up Work | 6 | 0
P2 - nice to have | 4 | 0 | 0 | 4 | 0% |  | C - AI-Assisted First Pass | 5 | 0
All stories | 59 | 1 | 15 | 53 | 1.695% |  | D - Review & Cross-Validation | 8 | 0
[7 empty] | E - Disagreement & Dispute | 6 | 0
[7 empty] | F - Provenance & History | 5 | 0
[7 empty] | G - Roles, Permissions & Organisations | 5 | 0
[7 empty] | H - Release & Export | 6 | 0
[7 empty] | I - Evaluation | 5 | 0
[7 empty] | J - Organisations & Dashboard | 4 | 0
[7 empty] | K - Evidence & Handover | 4 | 0
Waiting for a ticket | [5 empty] | Committed stories with nothing on the board. Nobody is working on these, because there is nothing to pick up.
None | Every committed story that is not dropped has at least one ticket on the board.
Dropped | 6 stories the team dropped, so no ticket is expected: A1 A5 K1 K2 K3 K4
Workload by person | [5 empty] | Issues assigned on the board, beside PRs actually logged. Both count the same eight people.
Member | Assigned | To do | Doing | In review | Done | In sprint | Bundles touched | PRs logged | Reviews
Michael Max | 2 | 0 | 2 | 0 | 0 | 2 | AI provider & failures | 0 | 0
Parth | 2 | 0 | 2 | 0 | 0 | 2 | Annotation page & judgement | 0 | 0
Jingwei Lin | 3 | 0 | 2 | 1 | 0 | 3 | Review, permissions & dispute, Task & item backend | 1 | 1
Hanchen Wang | 5 | 0 | 4 | 0 | 1 | 5 | Draft ownership & verdict, Unallocated | 1 | 1
Yi Geng | 2 | 0 | 2 | 0 | 0 | 2 | Draft ownership & verdict, Unallocated | 1 | 1
Dishank Aswal | 1 | 0 | 1 | 0 | 0 | 1 | Task & item backend | 0 | 0
Kanishka Kathait | 2 | 0 | 2 | 0 | 0 | 2 | Task & item backend | 0 | 0
Tok Tin Chung | 1 | 0 | 1 | 0 | 0 | 1 | Project setup & status UI | 0 | 0
Nobody assigned | 55 | 55 of 73 issues on the board have no owner - including every Evaluation issue and the whole AI task queue.
Every issue on the board
Issue | Type | Status | Assignee | Sprint | Jira epic | Summary | Backlog story | Matched from | PRs
SCRUM-1 | Task | To Do |  |  | AI Annotation Pipeline | Task queue: Create AI batch job and per-item job status models | C2 | description | 0
SCRUM-2 | Task | To Do |  |  | AI Annotation Pipeline | Task queue: Execute task annotation asynchronously through a worker | C2 | description | 0
SCRUM-3 | Task | To Do |  |  | AI Annotation Pipeline | Task queue: Retry failed items and preserve permanent failures | C2 | description | 0
SCRUM-4 | Subtask | To Do |  |  |  | Subtask 2.1 |  |  | 0
SCRUM-5 | Task | To Do |  |  | AI Annotation Pipeline | Task queue: Display batch progress and per-item job status | C2 | description | 0
SCRUM-6 | Task | In Progress | Yi Geng | W6 | Annotation & Human Judgement | AI-Provider: Integrate labeling_ai_assistnat_mvp as an AI provider | C1 | description | 0
SCRUM-7 | Task | In Progress | Michael Max | W6 | Annotation & Human Judgement | AI-Provider: Stop generating fake annotations when the AI provider fails | C3 | description | 0
SCRUM-8 | Task | In Progress | Tok Tin Chung | W6 | Organisation Management | Organisation management: Invitation & acceptance | G5 | description | 0
SCRUM-20 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Project & Policy: Configure project review and annotation policies | B2 | description | 0
SCRUM-21 | Task | In Progress | Jingwei Lin | W6 | Project, Policy & Task Lifecycle | Task Lifecycle: Prevent cross-project task and task-item writes | G3 | description | 0
SCRUM-22 | Task | In Progress | Dishank Aswal | W6 | Project, Policy & Task Lifecycle | Task Lifecycle: Validate task-item status before database commit | G4 | description | 0
SCRUM-23 | Task | In Progress | Kanishka Kathait | W6 | Project, Policy & Task Lifecycle | Task Lifecycle: Preserve lifecycle conflict responses as HTTP 409 | B5 | description | 0
SCRUM-24 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Task Lifecycle: Implement valid task lifecycle transitions | B4 | description | 0
SCRUM-25 | Task | In Progress | Hanchen Wang | W6 | Annotation & Human Judgement | Annotation: Enforce draft ownership | D6 | description | 0
SCRUM-26 | Task | In Progress | Hanchen Wang | W6 | Annotation & Human Judgement | Annotation: Make draft submission and annotation creation atomic | D5 | description | 0
SCRUM-27 | Task | To Do |  |  | Review, Dispute & Adjudication | Review / Annotation: Reviewer should be able to select the correct submitted annotation | D4 | description | 0
SCRUM-28 | Task | In Progress | Yi Geng | W6 | Annotation & Human Judgement | Annotation: Preventing finalized annotations from being overwritten | D5 | description | 0
SCRUM-29 | Task | In Progress | Jingwei Lin | W6 | Review, Dispute & Adjudication | Review: Retire or restrict legacy review mutation endpoints | D2 | description | 0
SCRUM-30 | Task | In Progress | Michael Max | W6 | Annotation & Human Judgement | AI-Provider: Store & Display AI suggestions, failures and unavailable states | C3 | description | 0
SCRUM-31 | Task | In Progress | Parth | W6 | Review, Dispute & Adjudication | Review: Record verdict, feedback & justification | C5 | description | 0
SCRUM-32 | Task | To Do |  |  | Review, Dispute & Adjudication | Review: Persist reviewer corrections as structured data | D3 | description | 0
SCRUM-34 | Task | In Progress | Kanishka Kathait | W6 | Project, Policy & Task Lifecycle | Task Lifecycle: Make dataset registration transactional | B5 | description | 0
SCRUM-35 | Task | In Progress | Parth | W6 | Review, Dispute & Adjudication | Dispute / Annotation: Implement "Dispute & send back to annotator" | E2 | description | 0
SCRUM-36 | Task | To Do |  |  | Review, Dispute & Adjudication | Dispute: Basic Functionality | E1, E3, E4, E5, E6 | description | 0
SCRUM-37 | Task | To Do |  |  | Provenance & Audit History | Provenance: Guarantee one canonical answer per task item | H4 | description | 0
SCRUM-38 | Task | To Do |  |  | Provenance & Audit History | Provenance: Preserve AI, annotator, reviewer and adjudicator outputs separately | F3 | description | 0
SCRUM-39 | Task | To Do |  |  | Provenance & Audit History | Provenance: Item-level provenance timeline | F1, F5 | both | 0
SCRUM-40 | Task | To Do |  |  | Provenance & Audit History | Provenance: Record correct audit actor types | F4 | description | 0
SCRUM-41 | Task | To Do |  |  | Provenance & Audit History | Provenance: Remove duplicate escalation audit changes | F4 | description | 0
SCRUM-42 | Task | To Do |  |  | Dataset Release & Export | Release & Export: Basic functionality | H1, H2, H3, H6 | both | 0
SCRUM-43 | Task | To Do |  |  | Dataset Release & Export | Release & Export: Align task completion and export readiness | B6, H5 | backlog CSV | 0
SCRUM-44 | Task | In Review | Jingwei Lin | W6 | Organisation Management | Organisation Management: Users can only perform actions that are permitted by their roles. | G1 | description | 1
SCRUM-45 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Project lifecycle: Update and archive a project | J4 | description | 0
SCRUM-46 | Task | To Do |  |  | AI Annotation Pipeline | Task queue: Trigger an AI run and route completed items to review | C2 | description | 0
SCRUM-47 | Task | To Do |  |  | Annotation & Human Judgement | Annotation: Connect the existing text annotation page to live APIs |  |  | 0
SCRUM-48 | Task | To Do |  |  | Review, Dispute & Adjudication | Review: Assign or claim work and provide role queues | D8 | description | 0
SCRUM-49 | Task | To Do |  |  | Review, Dispute & Adjudication | Review: Execute accept, adjust, reject and dispute transitions | C5, D3, E1 | description | 0
SCRUM-50 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Policy: Apply configured governance rules | B2, G2 | description | 0
SCRUM-51 | Task | To Do |  |  | Review, Dispute & Adjudication | Review: Independent second reviewer | D7, E1 | description | 0
SCRUM-52 | Task | To Do |  |  | Review, Dispute & Adjudication | Dispute: Adjudicator queue and authorization | D8, E3, E6, G1 | description | 0
SCRUM-53 | Task | To Do |  |  | Provenance & Audit History | Provenance: Source versioning | F2 | description | 0
SCRUM-54 | Subtask | To Do |  | W6 | Annotation & Human Judgement | Define the AnnotationAssistant interface | C1 | parent ticket | 0
SCRUM-55 | Subtask | To Do |  | W6 | Annotation & Human Judgement | Replace the Gemini call with an OpenAI-compatible client | C1 | parent ticket | 0
SCRUM-56 | Subtask | To Do |  | W6 | Annotation & Human Judgement | Port the MVP's four text tasks behind the interface | C1 | parent ticket | 0
SCRUM-57 | Subtask | To Do |  |  | Review, Dispute & Adjudication | Dispute: Detect reviewer disagreement automatically | E1, E3, E4, E5, E6 | parent ticket | 0
SCRUM-58 | Subtask | To Do |  |  | Review, Dispute & Adjudication | Dispute: Record an expert adjudication as its own decision | E1, E3, E4, E5, E6 | parent ticket | 0
SCRUM-59 | Subtask | To Do |  |  | Review, Dispute & Adjudication | Dispute: Keep the disagreement after the dispute is resolved | E1, E3, E4, E5, E6 | parent ticket | 0
SCRUM-60 | Subtask | To Do |  |  | Review, Dispute & Adjudication | Dispute: Make the escalation posture configurable and enforced | E1, E3, E4, E5, E6 | parent ticket | 0
SCRUM-61 | Subtask | To Do |  |  | Review, Dispute & Adjudication | Dispute: Connect the dispute and arbitration screens | E1, E3, E4, E5, E6 | parent ticket | 0
SCRUM-62 | Subtask | To Do |  |  | Provenance & Audit History | Provenance: Record the production history of every label | F1 | parent ticket | 0
SCRUM-63 | Subtask | To Do |  |  | Provenance & Audit History | Provenance: Show an item's whole timeline on one screen | F1 | parent ticket | 0
SCRUM-64 | Subtask | To Do |  |  | Dataset Release & Export | Release: Create an immutable release artefact | H1 | parent ticket | 0
SCRUM-65 | Subtask | To Do |  |  | Dataset Release & Export | Release: Produce a manifest for every release | H1 | parent ticket | 0
SCRUM-66 | Subtask | To Do |  |  | Dataset Release & Export | Release: Refuse a release that fails its pre-release checks | H1 | parent ticket | 0
SCRUM-67 | Subtask | To Do |  |  | Dataset Release & Export | Release: Show real releases, policy and history on the project screens | H1 | parent ticket | 0
SCRUM-68 | Task | In Progress |  |  | Evaluation Harness and Casebook | Evaluation1: Scenario harness that drives the workflow end to end | I1 | description | 0
SCRUM-69 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation2: Repeatable runs and regression reporting | I1 | description | 0
SCRUM-70 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation3: Casebook structure and the adversarial categories | I2 | description | 0
SCRUM-71 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation4: Grow the casebook to 40–60 cases | I2 | description | 0
SCRUM-72 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation5: Reviewer agreement and AI suggestion quality | I3 | description | 0
SCRUM-73 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation6: Measure what AI assistance does to human judgement | I4 | description | 0
SCRUM-74 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation7: Integrity checks on provenance, roles and releases | I5 | description | 0
SCRUM-75 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation8: Findings record including negative results | I5 | description | 0
SCRUM-81 | Task | In Progress | Hanchen Wang | W6 | Trustworthy Foundations | Schema: Fix db setup issues | A3 | description | 0
SCRUM-82 | Task | Done | Hanchen Wang | W6 | Trustworthy Foundations | Schema: Restore existing testcases | A2 | description | 1
SCRUM-84 | Task | In Progress | Hanchen Wang | W6 | Trustworthy Foundations | Schema: Replace hardcoded credentials | A4 | description | 0
SCRUM-85 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Task lifecycle: Create annotation and judgement tasks with a result shape | B3 | description | 0
SCRUM-86 | Task | To Do |  |  | Review, Dispute & Adjudication | Review: Prevent self-review of own annotations | D1 | description | 0
SCRUM-87 | Task | To Do |  |  | Annotation & Human Judgement | Annotation: Configurable AI suggestion visibility | C4 | description | 0
SCRUM-88 | Task | To Do |  |  | Organisation Management | Organisation Management: Stable organisation identifier and URL | J1 | description | 0
SCRUM-89 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Project: Overview of status and progress | J2 | description | 0
SCRUM-90 | Task | To Do |  |  | Organisation Management | Organisation Management: Invite, remove and role-manage members | J3 | description | 0
SCRUM-91 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Project lifecycle: Create a project scoped to an organisation | B1 | description | 0

## Client Report
Client Report
Set the two dates below. Everything else recalculates for that period - ready to paste into the Status Checking form or the weekly client meeting.
Reporting period starts | 2026-08-26 | <- type the two dates here
Reporting period ends | 2026-09-16
This period at a glance |  |  | Delivery by epic, this period
PRs merged | 3 |  | Epic | PRs | Stories done
Members who merged | 3 |  | A - Trustworthy Foundations | 1 | 1
Stories completed | 2 |  | B - Setting Up Work | 0 | 0
Defect-fix PRs | 0 |  | C - AI-Assisted First Pass | 0 | 0
Feature PRs | 1 |  | D - Review & Cross-Validation | 0 | 0
PRs reviewed by a second person | 2 |  | E - Disagreement & Dispute | 0 | 0
|  |  | F - Provenance & History | 0 | 0
|  |  | G - Roles, Permissions & Organisations | 1 | 1
|  |  | H - Release & Export | 0 | 0
Individual contribution, this period |  |  | I - Evaluation | 0 | 0
Member | PRs | Reviews given | Stories completed | Main area | What they delivered (write this before the client meeting)
Michael Max | 0 | 0 | 0 | 0 | 0
Parth | 0 | 0 | 0
Jingwei Lin | 1 | 1 | 1
Hanchen Wang | 1 | 1 | 1
Yi Geng | 1 | 1 | 0
Dishank Aswal | 0 | 0 | 0
Kanishka Kathait | 0 | 0 | 0
Tok Tin Chung | 0 | 0 | 0
Narrative for the Status Checking form |  |  | Cream cells are written by the leads before each client meeting. The numbers above are the evidence behind them.
Progress and achievements
Obstacles and risks
Next steps and milestones
Decisions needed from the client

## Lists
Members | Week 1 Monday | Work type | Area / repo | Story complete? | Epic | Story ID | Epic | Priority | Role | Story title | SCRUM ticket(s) | Week | Starts (Mon) | Ends (Sun) | Work bundle | Jira status | SCRUM ticket
Michael Max | 2026-08-03 | Feature | hej-web (frontend) | Yes - story complete | A | - |  |  |  | (not tied to a backlog story) |  | W1 | 2026-08-03 | 2026-08-09 |  |  | SCRUM-1
Parth | Check this date once, then leave it alone. | Defect fix | hej-api (backend) | No - more work to come | B | A1 | A | P0 | Lead | Changes are reviewed before they reach the platform |  | W2 | 2026-08-10 | 2026-08-16 | Unallocated | Dropped | SCRUM-2
Jingwei Lin | Every Week number is counted from here. | Refactor | packages/ui | N/A - not story work | C | A2 | A | P0 | SC | I can trust that a fix in one place hasn't broken another | SCRUM-82 | W3 | 2026-08-17 | 2026-08-23 | Unallocated | Done | SCRUM-3
Hanchen Wang | To check it: look at the week calendar in columns T-V. | Tests | labeling_ai_assistnat_mvp (AI) |  | D | A3 | A | P0 | SC | I can get a working copy of the platform running by myself | SCRUM-81 | W4 | 2026-08-24 | 2026-08-30 | Unallocated | In progress | SCRUM-4
Yi Geng | W6 should read Mon 7 Sep 2026, and W13 should be the last week. | Documentation | Database / schema |  | E | A4 | A | P0 | SC | Platform credentials aren't sitting in shared code | SCRUM-84 | W5 | 2026-08-31 | 2026-09-06 | Unallocated | In progress | SCRUM-5
Dishank Aswal |  | Spike / Research | CI / tooling |  | F | A5 | A | P0 | SC | A status means the same thing wherever I see it |  | W6 | 2026-09-07 | 2026-09-13 | Unallocated | Dropped | SCRUM-6
Kanishka Kathait |  | DevOps / CI | Docs / report |  | G | B1 | B | P0 | BE/FE | I can create a project to hold related work | SCRUM-91 | W7 | 2026-09-14 | 2026-09-20 | Project setup & status UI | To Do | SCRUM-7
Tok Tin Chung |  | Client / PM / Report | Other |  | H | B2 | B | P0 | BE | I can decide how carefully my project's work gets reviewed | SCRUM-20, SCRUM-50 | W8 | 2026-09-21 | 2026-09-27 | Project setup & status UI | To Do | SCRUM-8
[5 empty] | I | B3 | B | P0 | BE/FE | I can create a task for a specific piece of work | SCRUM-85 | W9 | 2026-09-28 | 2026-10-04 | Project setup & status UI | To Do | SCRUM-20
[5 empty] | J | B4 | B | P0 | BE | My task moves through real states, not just “draft” | SCRUM-24 | W10 | 2026-10-05 | 2026-10-11 | Task & item backend | To Do | SCRUM-21
[5 empty] | K | B5 | B | P0 | BE | Loading a dataset either works or leaves nothing behind | SCRUM-23, SCRUM-34 | W11 | 2026-10-12 | 2026-10-18 | Task & item backend | In progress | SCRUM-22
[6 empty] | B6 | B | P1 | BE | “Done” means the same thing everywhere I look | SCRUM-43 | W12 | 2026-10-19 | 2026-10-25 | Audit & history | To Do | SCRUM-23
[6 empty] | C1 | C | P1 | BE | The AI assistant can be swapped without disrupting my work | SCRUM-6 | W13 | 2026-10-26 | 2026-11-01 | Unallocated | In progress | SCRUM-24
[6 empty] | C2 | C | P0 | BE | A large batch of items gets AI-annotated reliably | SCRUM-1, SCRUM-2, SCRUM-3, SCRUM-5, SCRUM-46 | End |  | 2026-11-01 | AI task queue | To Do | SCRUM-25
[6 empty] | C3 | C | P0 | BE | I'm told when the AI failed instead of being shown a fake answer | SCRUM-7, SCRUM-30 | Project ends at the close of W13. |  |  | AI provider & failures | In progress | SCRUM-26
[6 empty] | C4 | C | P1 | BE/FE | I can control whether reviewers see the AI's answer first | SCRUM-87 |  |  |  | Annotation page & judgement | To Do | SCRUM-27
[6 empty] | C5 | C | P1 | BE/FE | I can record why I decided, not just what I decided | SCRUM-31, SCRUM-49 |  |  |  | Annotation page & judgement | In progress | SCRUM-28
[6 empty] | D1 | D | P0 | BE | I can't approve my own work | SCRUM-86 |  |  |  | Review, permissions & dispute | To Do | SCRUM-29
[6 empty] | D2 | D | P0 | BE | Approval history can't be rewritten behind my back | SCRUM-29 |  |  |  | Review, permissions & dispute | In progress | SCRUM-30
[6 empty] | D3 | D | P0 | BE | The correction I make is the answer that gets saved | SCRUM-32, SCRUM-49 |  |  |  | Review, permissions & dispute | To Do | SCRUM-31
[6 empty] | D4 | D | P0 | BE | I know I'm reviewing the right person's work | SCRUM-27 |  |  |  | Draft ownership & verdict | To Do | SCRUM-32
[6 empty] | D5 | D | P0 | BE | Finalised means finalised | SCRUM-26, SCRUM-28 |  |  |  | Draft ownership & verdict | In progress | SCRUM-34
[6 empty] | D6 | D | P0 | BE | My unfinished work is mine | SCRUM-25 |  |  |  | Draft ownership & verdict | In progress | SCRUM-35
[6 empty] | D7 | D | P1 | BE | A defined share of items gets independently double-checked | SCRUM-51 |  |  |  | Annotation page & judgement | To Do | SCRUM-36
[6 empty] | D8 | D | P0 | BE/FE | Work reaches the right person | SCRUM-48, SCRUM-52 |  |  |  | Annotation page & judgement | To Do | SCRUM-37
[6 empty] | E1 | E | P0 | BE | Disagreement is noticed without anyone reporting it | SCRUM-36, SCRUM-49, SCRUM-51 |  |  |  | Review, permissions & dispute | To Do | SCRUM-38
[6 empty] | E2 | E | P0 | FE | I can send an item back to the annotator | SCRUM-35 |  |  |  | Annotation page & judgement | In progress | SCRUM-39
[6 empty] | E3 | E | P1 | BE | An expert's decision is recorded as its own decision | SCRUM-36, SCRUM-52 |  |  |  | Review, permissions & dispute | To Do | SCRUM-40
[6 empty] | E4 | E | P1 | BE | Resolving a dispute doesn't erase the disagreement | SCRUM-36 |  |  |  | Review, permissions & dispute | To Do | SCRUM-41
[6 empty] | E5 | E | P1 | BE | Escalation matches the assurance my project needs | SCRUM-36 |  |  |  | Review, permissions & dispute | To Do | SCRUM-42
[6 empty] | E6 | E | P0 | FE | The dispute and arbitration screens show my real cases | SCRUM-36, SCRUM-52 |  |  |  | Annotation page & judgement | To Do | SCRUM-43
[6 empty] | F1 | F | P0 | BE | I can ask how any label came to exist | SCRUM-39 |  |  |  | Audit & history | To Do | SCRUM-44
[6 empty] | F2 | F | P1 | BE | Annotations remember which guideline they followed | SCRUM-53 |  |  |  | Unallocated | To Do | SCRUM-45
[6 empty] | F3 | F | P0 | BE | The AI's suggestion, the human's answer and the reviewer's correction stay separate | SCRUM-38 |  |  |  | Audit & history | To Do | SCRUM-46
[6 empty] | F4 | F | P1 | BE | History tells me who really did what | SCRUM-40, SCRUM-41 |  |  |  | Audit & history | To Do | SCRUM-47
[6 empty] | F5 | F | P1 | FE | I can see an item's whole story on one screen | SCRUM-39 |  |  |  | Unallocated | To Do | SCRUM-48
[6 empty] | G1 | G | P0 | BE | My role determines what I can do | SCRUM-44, SCRUM-52 |  |  |  | Review, permissions & dispute | In progress | SCRUM-49
[6 empty] | G2 | G | P1 | BE | My project's governance posture actually governs | SCRUM-50 |  |  |  | Unallocated | To Do | SCRUM-50
[6 empty] | G3 | G | P0 | BE | My work stays inside my project | SCRUM-21 |  |  |  | Task & item backend | In progress | SCRUM-51
[6 empty] | G4 | G | P1 | BE/SC | The platform refuses states that can't exist | SCRUM-22 |  |  |  | Task & item backend | In progress | SCRUM-52
[6 empty] | G5 | G | P0 | BE | I can actually invite someone into my organisation | SCRUM-8 |  |  |  | Project setup & status UI | In progress | SCRUM-53
[6 empty] | H1 | H | P0 | BE | A release is a fixed thing I can point at | SCRUM-42 |  |  |  | Release & export | To Do | SCRUM-54
[6 empty] | H2 | H | P0 | BE | Every release explains what's in it | SCRUM-42 |  |  |  | Release & export | To Do | SCRUM-55
[6 empty] | H3 | H | P0 | BE | A release that shouldn't exist is refused | SCRUM-42 |  |  |  | Release & export | To Do | SCRUM-56
[6 empty] | H4 | H | P0 | BE | Every released item has exactly one authoritative answer | SCRUM-37 |  |  |  | Release & export | To Do | SCRUM-57
[6 empty] | H5 | H | P1 | BE | Export figures agree with the rest of the platform | SCRUM-43 |  |  |  | Release & export | To Do | SCRUM-58
[6 empty] | H6 | H | P0 | FE | The export, policy and history screens show real data | SCRUM-42 |  |  |  | Unallocated | To Do | SCRUM-59
[6 empty] | I1 | I | P0 | GOV | I can re-run the whole workflow against known cases | SCRUM-68, SCRUM-69 |  |  |  | Unallocated | In progress | SCRUM-60
[6 empty] | I2 | I | P0 | GOV | The platform is tested against cases designed to break it | SCRUM-70, SCRUM-71 |  |  |  | Unallocated | To Do | SCRUM-61
[6 empty] | I3 | I | P1 | GOV | I can tell whether reviewers actually agree | SCRUM-72 |  |  |  | Unallocated | To Do | SCRUM-62
[6 empty] | I4 | I | P1 | GOV | I can see what AI assistance does to human judgement | SCRUM-73 |  |  |  | Unallocated | To Do | SCRUM-63
[6 empty] | I5 | I | P1 | GOV | I can prove the platform's records hold up | SCRUM-74, SCRUM-75 |  |  |  | Unallocated | To Do | SCRUM-64
[6 empty] | J1 | J | P2 | BE | My organisation has a stable identity | SCRUM-88 |  |  |  | Project setup & status UI | To Do | SCRUM-65
[6 empty] | J2 | J | P2 | FE | I can see how my project is going at a glance | SCRUM-89 |  |  |  | Unallocated | To Do | SCRUM-66
[6 empty] | J3 | J | P2 | BE/FE | I can invite and manage my team | SCRUM-90 |  |  |  | Project setup & status UI | To Do | SCRUM-67
[6 empty] | J4 | J | P2 | BE/FE | I can maintain a project after creating it | SCRUM-45 |  |  |  | Project setup & status UI | To Do | SCRUM-68
[6 empty] | K1 | K | P1 | Lead | A reader can understand the system without us in the room |  |  |  |  | Unallocated | Dropped | SCRUM-69
[6 empty] | K2 | K | P1 | all | Each of us can defend our own design decisions |  |  |  |  | Unallocated | Dropped | SCRUM-70
[6 empty] | K3 | K | P1 | GOV | What didn't work is recorded as carefully as what did |  |  |  |  | Unallocated | Dropped | SCRUM-71
[6 empty] | K4 | K | P0 | Lead | The end-to-end demonstration works when it matters |  |  |  |  | Unallocated | Dropped | SCRUM-72
SCRUM-73
SCRUM-74
SCRUM-75
SCRUM-81
SCRUM-82
SCRUM-84
SCRUM-85
SCRUM-86
SCRUM-87
SCRUM-88
SCRUM-89
SCRUM-90
SCRUM-91