## Start Here
CS-57 - Contribution Tracker
Human-AI Data Annotation, Provenance & Dataset Evaluation Platform ¦ Group CS-57 ¦ Client: Hunter Xu
The one rule
After your pull request is merged into main, add ONE row to the 'Contribution Log' tab. That is the whole process. Every other tab fills itself in from those rows.
What each tab is for
Contribution Log | The only tab you type into. One row per merged PR. Cream headers = you fill in; grey headers = filled in automatically, do not type in them.
Dashboard | Automatic. Who merged what, per week and in total; review health; the split across frontend / backend / AI.
Jira Statistics | Who owns which bundle, how much of the committed scope is done, workload per person, and every issue on the board matched to the story it serves. Fill in the nine Owner cells once; the rest is a snapshot of docs/Jira.csv plus live PR counts.
Client Report | Set a date range at the top and this becomes the numbers block for the Status Checking form and the weekly client meeting.
Lists | Reference data behind the dropdowns and the automatic columns. Only edit the Week 1 Monday date, and only once.
When you finish a story
Work through this before you ask for a review. If you cannot tick items 1 and 2, the story is not finished - which is fine, but log the PR with 'Story complete? = No'.
1. Open the story in user-stories.html and re-read its acceptance criteria - every numbered criterion, not the one you remember. This is what 'done' means for that story.
2. The checks pass: npm run typecheck and the test suite run clean in whatever you touched (story A2).
3. There is a test covering the behaviour you changed, not only the code you wrote.
4. Anything a teammate could not guess is written down - a change note, and a decision record if you chose between real alternatives.
5. Open the PR with the story ID in the title, e.g. 'C2 - task queue progress'.
6. Request review from someone who did not write the code (story A1), and move the SCRUM ticket to In Review.
7. Once it is merged: move the SCRUM ticket to Done, then add your row to the Contribution Log.
8. Set 'Story complete? = Yes' only if every acceptance criterion is now met. If it closed a catalogued defect, put the issue number in 'Defects closed'.
How to log a merged PR
1. Open 'Contribution Log' and go to the first empty row.
2. Date merged - the date the PR landed on main. The Week column fills itself in from this.
3. Member is you. Reviewed by is the teammate who approved the PR. They must be different people (story A1 - no change reaches main without a second person's review); the sheet turns the row red if they are not.
4. Story ID - pick the backlog story the work serves (A1 ... K4). The story title, epic and priority appear automatically.
5. What changed - one sentence a non-engineer can understand. This sentence is what gets read out to the client, so write it for the client, not for the team.
6. Story complete? - answer 'Yes' only when nothing further is needed for that story. This is what drives every progress number in the workbook.
What a good row looks like
| Date merged | Member | Reviewed by | Work type | Story ID | What changed (plain English, for the client) | Story complete?
| 2026-09-08 | Hanchen Wang | Michael Max | Feature | C2 | A task with 1,000 items now runs in the background and shows a live progress bar, instead of freezing the page. | No - more work to come
| 2026-09-09 | Yi Geng | Dishank Aswal | Defect fix | C3 | When the AI is unavailable the item is now marked 'AI failed' instead of being filled with an invented bounding box. | Yes - story complete
| 2026-09-10 | Parth | Tok Tin Chung | Client / PM / Report | K2 | Wrote up the Week 6 status report and the client's decision on dispute routing. | N/A - not story work
Note what the summaries do not say: no file names, no function names, no ticket jargon. Write the sentence the client would understand if it were read out loud.
Ground rules
- One row per merged PR - not per commit, and not per day of work.
- Log it the same day it merges. A log reconstructed from memory in Week 12 is worth very little to anyone, including you.
- Never delete or reorder someone else's row. If a row is wrong, correct that row.
- Do not insert, delete or reorder columns. The other tabs read this one by column position and will break.
- Work that is not a PR still counts - client meetings, the report, the proposal, research spikes. Log it with work type 'Client / PM / Report' or 'Spike / Research' and leave the PR number blank.
- If one PR serves two stories, log the row against the main story and name the second one in Notes.

## Contribution Log
Date | Week | Member | Reviewed by | Review OK? | SCRUM ticket | PR # | PR link | Work type | Area / repo | Story ID | Story title | Epic | Pri | Defects closed | What changed (plain English, for the client) | Story complete? | Notes / evidence
2026-08-28 | W4 | Yi Geng | Yi Geng | SELF-REVIEW | - | 1 | https://github.com/USYD-CS-Capstone/hej/pull/1 | Refactor | Other | - | (not tied to a backlog story) | - | - | - | Copy the branch name 'week13' (previous team's latest progress) to the main branch | N/A - not story work
2026-09-07 | W6 | Hanchen Wang | Jingwei Lin | OK | SCRUM-82 | 2 | https://github.com/USYD-CS-Capstone/hej/pull/2 | DevOps / CI | CI / tooling | A2 | I can trust that a fix in one place hasn't broken another | A | P0 | 12,13,25,26 | Enable existing testing scripts, so changes can be verified before merging again. | Yes - story complete
2026-09-07 | W6 | Jingwei Lin | Hanchen Wang | OK | SCRUM-44 | 4 | https://github.com/USYD-CS-Capstone/hej/pull/4 | Feature | hej-api (backend) | G1 | Users can now only do what their role allows. | G | P0 | 7 | Users now can only perform actions that the role allowed them to do. | Yes - story complete
2026-09-12 | W6 | Jingwei Lin | Hanchen Wang | OK | SCRUM-29 | 6 | https://github.com/USYD-CS-Capstone/hej/pull/6 | Defect fix | hej-api (backend) | D2 | Approval history can't be rewritten behind my back | D | P0 | 8 | Retires the legacy review mutation endpoints that allowed approval history to be changed or deleted without updating the corresponding task-item state. | No - more work to come
2026-09-12 | W6 | Michael Max | Yi Geng | OK | SCRUM-30 | 7 | https://github.com/USYD-CS-Capstone/hej/pull/7 | Defect fix | hej-web (frontend) | C3 | I'm told when the AI failed instead of being shown a fake answer | C | P0 | 20 | When the AI provider fails, the item is now marked as an AI failure instead of being filled with an invented answer, and the task screen shows each item's AI run status. | Yes - story complete | Also covers SCRUM-7.
2026-09-12 | W6 | Michael Max | Yi Geng | OK | SCRUM-6 | 8 | https://github.com/USYD-CS-Capstone/hej/pull/8 | Feature | labeling_ai_assistnat_mvp (AI) | C1 | The AI assistant can be swapped without disrupting my work | C | P1 | - | Connected the platform to the team's AI annotation service for text, image, audio and video through one provider interface, so the AI model can be swapped without changing how people work. | No - more work to come
2026-09-12 | W6 | Dishank Aswal | Jingwei Lin | OK | SCRUM-22 | 9 | https://github.com/USYD-CS-Capstone/hej/pull/9 | Defect fix | hej-api (backend) | G4 | The platform refuses states that can't exist | G | P1 | 10 | Fixed task status validation and updated the allowed final statuses. | Yes - story complete
2026-09-12 | W6 | Dishank Aswal | Jingwei Lin | OK | SCRUM-23 | 9 | https://github.com/USYD-CS-Capstone/hej/pull/9 | Refactor | hej-api (backend) | B5 | Loading a dataset either works or leaves nothing behind | B | P0 | 29 | Preserved task lifecycle conflict responses as HTTP 409 instead of returning 500 errors. | No - more work to come
2026-09-12 | W6 | Michael Max | Yi Geng | OK | SCRUM-81 | 10 | https://github.com/USYD-CS-Capstone/hej/pull/10 | Defect fix | hej-api (backend) | A3 | I can get a working copy of the platform running by myself | A | P0 | 23, 24 | Settings and credentials now load from a local .env file instead of being hard-coded, and the database reset script can be run again without breaking the setup. | No - more work to come | Also covers SCRUM-84.
2026-09-12 | W6 | Kanishka Kathait | Jingwei Lin | OK | SCRUM-34 | 11 | https://github.com/USYD-CS-Capstone/hej/pull/11 | Defect fix | hej-api (backend) | B5 | Loading a dataset either works or leaves nothing behind | B | P0 | 16 | Made dataset registration transactional to prevent partial data when AI fails. Added success and rollback tests. | Yes - story complete
2026-09-12 | W6 | Hanchen Wang | Yi Geng | OK | SCRUM-25 | 13 | https://github.com/USYD-CS-Capstone/hej/pull/13 | Defect fix | hej-web (frontend) | D6 | My unfinished work is mine | D | P0 | 6 | Enfored draft ownership (1 item - 1 annotator) unfinished draft belongs to its author, otherwise read-only. | Yes - story complete
2026-09-13 | W6 | Jingwei Lin | Michael Max | OK | SCRUM-21 | 14 | https://github.com/USYD-CS-Capstone/hej/pull/14 | Defect fix | hej-api (backend) | G3 | My work stays inside my project | G | P0 | 9 | A task can now only be changed through the project it belongs to, so a request made under one project can't edit another project's tasks. | Yes - story complete
2026-09-14 | W7 | Tim Chung | Jingwei Lin | OK | SCRUM-8 | 16 | https://github.com/USYD-CS-Capstone/hej/pull/16 | Feature | hej-api (backend) | G5 | I can actually invite someone into my organisation | G | P0 | 17, 18 | Backend only: registered users can be invited to an organisation and accept invitations successfully. | Yes - story complete
2026-09-14 | W7 | Parth | Dishank Aswal | OK | SCRUM-35 | 17 | https://github.com/USYD-CS-Capstone/hej/pull/17 | Defect fix | hej-web (frontend) | E2 | I can send an item back to the annotator | E | P0 | 15 | User can send an item back to the annotator | Yes - story complete
2026-09-14 | W7 | Parth | Dishank Aswal | OK | SCRUM-31 | 17 | https://github.com/USYD-CS-Capstone/hej/pull/17 | Feature | hej-api (backend) | C5 | I can record why I decided, not just what I decided | C | P1 | - | I can record why I decided, not just what I decided | No - more work to come
2026-09-14 | W7 | Parth | Dishank Aswal | OK | - | 17 | https://github.com/USYD-CS-Capstone/hej/pull/17 | Feature | CI / tooling | - | (not tied to a backlog story) | - | - | - | Dockerize the application | N/A - not story work
2026-09-14 | W7 | Michael Max | Yi Geng | OK | SCRUM-81 | 18 | https://github.com/USYD-CS-Capstone/hej/pull/18 | Defect fix | hej-api (backend) | A3 | I can get a working copy of the platform running by myself | A | P0 | - | Setup now reports a failure with an error code instead of appearing to succeed, so a broken local install is noticed straight away. | Yes - story complete
2026-09-16 | W7 | Hanchen Wang | Dishank Aswal | OK | SCRUM-28 | 19 | https://github.com/USYD-CS-Capstone/hej/pull/19 | Defect fix | hej-api (backend) | D5 | Finalised means finalised | D | P0 | 2 | A finalised task item will not be mistakenly overwritten. | No - more work to come
2026-09-17 | W7 | Michael Max | Hanchen Wang | OK | SCRUM-2 | 20 | https://github.com/USYD-CS-Capstone/hej/pull/20 | Documentation | Docs / report | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Two proposal design docs for story C2 | No - more work to come
2026-09-17 | W7 | Michael Max | Hanchen Wang | OK | SCRUM-1 | 21 | https://github.com/USYD-CS-Capstone/hej/pull/21 | Feature | Database / schema | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Adds the two tables designed in #20: ai_batch_jobs and ai_item_jobs | No - more work to come
2026-09-18 | W7 | Michael Max | Hanchen Wang | OK | SCRUM-2 | 22 | https://github.com/USYD-CS-Capstone/hej/pull/22 | Feature | hej-api (backend) | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Moves the AI model call out of the dataset-registration request and into a worker process | No - more work to come
2026-09-19 | W7 | Hanchen Wang | Kanishka Kathait | OK | SCRUM-26 | 23 | https://github.com/USYD-CS-Capstone/hej/pull/23 | Defect fix | hej-api (backend) | D5 | Finalised means finalised | D | P0 | 11 | Make draft submission atomic; a transaction is all or nothing. | Yes - story complete
2026-09-20 | W7 | Parth | Hanchen Wang | OK | SCRUM-94 | 24 | https://github.com/USYD-CS-Capstone/hej/pull/24 | DevOps / CI | Database / schema | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | PostgreSQL is now the default database for native and Docker development. SQLite can still be selected explicitly through DATABASE_URL | No - more work to come | Co-reviewer: Yi Geng.
2026-09-20 | W7 | Jingwei Lin | Parth | OK | SCRUM-20 | 25 | https://github.com/USYD-CS-Capstone/hej/pull/25 | Feature | hej-web (frontend) | B2 | I can decide how carefully my project's work gets reviewed | B | P0 | - | Each project now has its own review and annotation policy, which sits between the organisation's defaults and an individual task's own settings. | No - more work to come
2026-09-20 | W7 | Dishank Aswal | Kanishka Kathait | OK | SCRUM-43 | 26 | https://github.com/USYD-CS-Capstone/hej/pull/26 | Defect fix | hej-api (backend) | B6 | “Done” means the same thing everywhere I look | B | P1 | 14, 19, 27 | Aligned task completion and export rules so only canonicalized items are treated as final and eligible for export. Centralised the eligibility check and updated the related tests. | Yes - story complete
2026-09-20 | W7 | Yi Geng | Jingwei Lin | OK | SCRUM-6 | 27 | https://github.com/USYD-CS-Capstone/hej/pull/27 | Feature | hej-web (frontend) | C1 | The AI assistant can be swapped without disrupting my work | C | P1 | - | Scrum-6 completed, implement Custom task & label definition & label list upload & schema driven AI output & label editing in project policy page | Yes - story complete
2026-09-21 | W7 | Tim Chung | Parth | OK | SCRUM-90 | 28 | https://github.com/USYD-CS-Capstone/hej/pull/28 | Feature | hej-api (backend) | J3 | I can invite and manage my team | J | P2 | - | Administrators can switch between organisations, invite members, see pending and expired invitations, remove members and change their roles on screen. Still in review. | No - more work to come | Co-reviewer: Hanchen Wang.
2026-09-21 | W8 | Michael Max | Hanchen Wang | OK | SCRUM-46 | 29 | https://github.com/USYD-CS-Capstone/hej/pull/29 | Feature | hej-api (backend) | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | A task owner can start an AI annotation run at any time, and each item the AI completes goes straight to human review as the AI's own submission. | No - more work to come
2026-09-21 | W8 | Michael Max | Hanchen Wang | OK | SCRUM-3 | 30 | https://github.com/USYD-CS-Capstone/hej/pull/30 | Feature | hej-api (backend) | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Temporary AI failures, such as rate limits, are now retried automatically, while permanent failures stop at once and stay visible on the item with the reason. | No - more work to come
2026-09-21 | W7 | Yi Geng | Michael Max | OK | - | 31 | https://github.com/USYD-CS-Capstone/hej/pull/31 | Defect fix | hej-api (backend) | - | (not tied to a backlog story) | - | - | - | Adaptation to PR#30, modify the annotation metadata structure, to add more detailed error_kind, error_code, error_type and error_message | N/A - not story work
2026-09-22 | Break | Michael Max | Yi Geng | OK | SCRUM-5 | 32 | https://github.com/USYD-CS-Capstone/hej/pull/32 | Feature | labeling_ai_assistnat_mvp (AI) | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | The task screen now shows each AI batch's progress and which items failed and why. This completes story C2. | Yes - story complete
2026-09-24 | W8 | Kanishka Kathait | Jingwei Lin | OK | SCRUM-48 | 33 | https://github.com/USYD-CS-Capstone/hej/pull/33 | Feature | hej-api (backend) | D8 | Work reaches the right person | D | P0 | - | Added self-served annotation, review and adjudication work queues with role checks, required annotator counts, submission limits and reviewer independence. | No - more work to come | Co-reviewer: Yi Geng.
2026-09-26 | W8 | Jingwei Lin | Hanchen Wang | OK | SCRUM-27 | 34 | https://github.com/USYD-CS-Capstone/hej/pull/34 | Defect fix | hej-api (backend) | D4 | I know I'm reviewing the right person's work | D | P0 | 3 | A reviewer's decision is now recorded against the specific annotator's submission they are looking at, instead of whichever one the system guessed. | No - more work to come
2026-09-26 | W8 | Hanchen Wang | Jingwei Lin | OK | SCRUM-48 | 35 | https://github.com/USYD-CS-Capstone/hej/pull/35 | Defect fix | hej-api (backend) | D8 | Work reaches the right person | D | P0 | - | Fixes to the new work queues: annotators cannot see each other's answers before submitting, AI-annotated items go straight to review, each submission is reviewed separately, and progress counts are shown. Still in review. | No - more work to come | Co-reviewer: Yi Geng.
2026-09-26 | W8 | Yi Geng | Hanchen Wang | OK | SCRUM-112 | 36 | https://github.com/USYD-CS-Capstone/hej/pull/36 | Feature | hej-api (backend) | B8 | My task chooses how people annotate it, not a hard-coded subtype | B | P2 | - | Task creation is reorganised around what the annotator sees and produces (input type, instructions, output format and annotation screen), and the AI model is now chosen at setup. | Yes - story complete
2026-09-26 | W8 | Jingwei Lin | Hanchen Wang | OK | SCRUM-50 | 37 | https://github.com/USYD-CS-Capstone/hej/pull/37 | Feature | hej-web (frontend) | G2 | My project's governance posture actually governs | G | P1 | - | A project's review policy is now enforced: it sets how many approvals an item needs, and every review decision must include a reason. | No - more work to come
2026-09-28 | W8 | Jingwei Lin | Hanchen Wang | OK | SCRUM-68 | 39 | https://github.com/USYD-CS-Capstone/hej/pull/39 | Tests | Other | I1 | I can re-run the whole workflow against known cases | I | P0 | - | An evaluation harness that runs the whole workflow through the platform as real users, from written test cases, and reports each case as pass or fail with the first step that failed. The first four cases are included. | No - more work to come | Still a draft.
2026-09-29 | W8 | Dishank Aswal | Hanchen Wang | OK | SCRUM-24 | 41 | https://github.com/USYD-CS-Capstone/hej/pull/41 | Defect fix | hej-api (backend) | B4 | My task moves through real states, not just “draft” | B | P0 | 28, 30 | Tasks can now be activated, paused, resumed, and completed through guarded manager actions. Dataset intake closes after activation, exports reflect work in progress, and deleting tasks or projects with retained work returns a clear error instead of failing. | Yes - story complete | Co-reviewer: Yi Geng.
2026-09-29 | W8 | Yi Geng | Hanchen Wang | OK | SCRUM-111 | 42 | https://github.com/USYD-CS-Capstone/hej/pull/42 | Feature | hej-web (frontend) | B7 | Task lifecycle: Import a JSONL dataset as one item per record | B | P1 | - | Record-based file inputs can be splited into multiple task items based on user-defined input projection, user can choose either entire record or one specific field in each record as input. | Yes - story complete
2026-09-29 | W8 | Hanchen Wang | Jingwei Lin | OK | SCRUM-114 | 43 | https://github.com/USYD-CS-Capstone/hej/pull/43 | Feature | hej-web (frontend) | D8 | Work reaches the right person | D | P0 | - | In the work panel, rework on a returned item is no longer lost when a draft is saved, a colleague's answer never appears in the annotation editor or item details, and a submission the platform refuses (the item is already full, or the AI has annotated it) is explained in the platform's own words. | No - more work to come
2026-09-29 | W8 | Hanchen Wang | Kanishka Kathait | OK | SCRUM-113 | 44 | https://github.com/USYD-CS-Capstone/hej/pull/44 | Feature | hej-web (frontend) | D4 | I know I'm reviewing the right person's work | D | P0 | - | A reviewer chooses which of an item's submissions to review, sees that submission's own answer, and the decision is recorded against it; the panel then moves to the next submission awaiting them. Item lists no longer show a colleague's name or answer. | Yes - story complete
2026-10-01 | Break | Jingwei Lin | Hanchen Wang | OK | SCRUM-116 | 45 | https://github.com/USYD-CS-Capstone/hej/pull/45 | Defect fix | hej-api (backend) | D1 | I can't approve my own work | D | P0 | 7 | The platform now refuses a review decision the reviewer isn't entitled to make, and says why. Nobody can decide on their own work or on an item they annotated, administrators included. Nobody can approve the same answer twice, decide on an item that is finished or in dispute, or send their own work to dispute. | No - more work to come | Issue 7 is only partly closed: it closes fully with SCRUM-99.
2026-10-01 | Break | Jingwei Lin | Hanchen Wang | OK | SCRUM-110 | 46 | https://github.com/USYD-CS-Capstone/hej/pull/46 | Feature | hej-web (frontend) | D9 | The project owner can deliberately reopen a finalised item | D | P1 | - | A reopened item no longer jumps back to "sent back by the expert" the next time the task page loads. A send-back from before the reopen no longer counts. | No - more work to come
2026-10-02 | Break | Hanchen Wang | Yi Geng | OK | SCRUM-38 | 47 | https://github.com/USYD-CS-Capstone/hej/pull/47 | Feature | hej-api (backend) | F3 | The AI's suggestion, the human's answer and the reviewer's correction stay separate | F | P0 | - | Every submitted answer, including each resubmission and each AI model's answer, is now kept as its own version and never overwritten, and an item can mark at most one version as its authoritative answer. | Yes - story complete
2026-10-04 | Break | Kanishka Kathait | Jingwei Lin | OK | SCRUM-93 | 49 | https://github.com/USYD-CS-Capstone/hej/pull/49 | Feature | hej-web (frontend) | D8 | Work reaches the right person | D | P0 | - | Annotators, reviewers and adjudicators now see live lists of the work their role allows, with each item's progress (for example 2 of 3 submitted), rework, and items that are already full. | No - more work to come
2026-10-04 | Break | Jingwei Lin | Hanchen Wang | OK | SCRUM-120 | 50 | https://github.com/USYD-CS-Capstone/hej/pull/50 | Defect fix | hej-api (backend) | D9 | The project owner can deliberately reopen a finalised item | D | P1 | - | A reopened item now stays open; before, it was switched back to "sent back by the expert" the next time anyone loaded the task's items. | Yes - story complete
2026-10-05 | Break | Dishank Aswal | Hanchen Wang | OK | SCRUM-117 | 52 | https://github.com/USYD-CS-Capstone/hej/pull/52 | Defect fix | hej-api (backend) | D8 | Work reaches the right person | D | P0 | - | Annotators can resubmit only their own returned, rejected, or adjudication-sent-back work. Approved and awaiting-review answers stay locked; queue editor permissions now match the API rule. | No - more work to come
2026-10-05 | Break | Parth | Jingwei Lin | OK | SCRUM-51 | 53 | https://github.com/USYD-CS-Capstone/hej/pull/53 | Feature | hej-api (backend) | D7 | A defined share of items gets independently double-checked | D | P1 | - | A second reviewer can't see the first reviewer's decision until they submit their own, a share of submissions is sampled for that independent second review, and an expert can no longer adjudicate work they annotated or reviewed. | Yes - story complete | With Scrum-52. Co-reviewer: Hanchen Wang, Jingwei Lin.
2026-10-05 | Break | Parth | Jingwei Lin | OK | SCRUM-52 | 53 | https://github.com/USYD-CS-Capstone/hej/pull/53 | Feature | hej-api (backend) | D8 | Dispute: Adjudicator queue and authorization | D | P1 | - | Implemented safeguards so adjudicators cannot handle disputes involving work they previously annotated, reviewed, or routed themselves, including administrators. Also ensured the adjudication queue and decision checks use the same rule, while keeping existing permission checks and second-review protections. | Yes - story complete | With Scrum-51. Co-reviewer: Hanchen Wang, Jingwei Lin.
2026-10-06 | Break | Hanchen Wang | Jingwei Lin | OK | SCRUM-119 | 54 | https://github.com/USYD-CS-Capstone/hej/pull/54 | Spike / Research | Other | A6 | A dataset-sized task opens without a wait | A | P1 | - | A task with hundreds of items opens about six times faster: each page now loads every item's saved drafts in one request instead of one per item (a 200-item page went from about 3.4 s to under 0.6 s). | No - more work to come | Co-reviewer: Yi Geng.
2026-10-06 | Break | Tim Chung | Jingwei Lin | OK | SCRUM-115 | 56 | https://github.com/USYD-CS-Capstone/hej/pull/56 | Feature | hej-web (frontend) | J3 | I can invite and manage my team | J | P2 | - | An invited person can now see their pending invitations and accept one in the app, and receives exactly the roles the administrator chose when inviting them. | Yes - story complete
2026-10-06 | Break | Jingwei Lin | Hanchen Wang | OK | SCRUM-41 | 57 | https://github.com/USYD-CS-Capstone/hej/pull/57 | Defect fix | hej-api (backend) | F4 | History tells me who really did what | F | P1 | 22 | The task history no longer repeats itself. An entry no longer lists, as a change, what its summary already says, and internal status codes no longer appear as an entry's description. Older entries read cleanly too. | No - more work to come
2026-10-07 | Break | Jingwei Lin | Yi Geng | OK | SCRUM-32 | 58 | https://github.com/USYD-CS-Capstone/hej/pull/58 | Feature | hej-api (backend) | D3 | The correction I make is the answer that gets saved | D | P0 | 5, 7 | Reviewer corrections stored as their own version (a proposal, never counted or approved); only on return/escalate, accept refused; visible only to the author, reviewers once decided, adjudicators and managers; panel sends it only when edited, and shows it to the annotator; ADR 012. | No - more work to come
2026-10-07 | Break | Jingwei Lin | Michael Max | OK | SCRUM-87 | 59 | https://github.com/USYD-CS-Capstone/hej/pull/59 | Feature | hej-api (backend) | C4 | I can control whether reviewers see the AI's answer first | C | P1 | - | Each item now records whether its work was done human-only or with AI assistance, fixed when the task is activated, so results from the two can be told apart afterwards. A task's annotation mode can't be changed once it's active. The AI only ever runs on items recorded as AI-assisted, so it never produces an answer on a human-only item. The mode is included in item lists and the export. | Yes - story complete
2026-10-07 | Break | Parth | Dishank Aswal | OK | SCRUM-109 | 60 | https://github.com/USYD-CS-Capstone/hej/pull/60 | Feature | hej-api (backend) | D2 | Approval history can't be rewritten behind my back | D | P0 | - | Implemented changes so item status always stays in sync with review and submission history. Status is now calculated from the full current workflow state, including multi-review, rework, AI submissions, and expert Return cases. | Yes - story complete
2026-10-08 | W9 | Jingwei Lin | Hanchen Wang | OK | SCRUM-85 | 61 | https://github.com/USYD-CS-Capstone/hej/pull/61 | Feature | hej-web (frontend) | B3 | I can create a task for a specific piece of work | B | P0 | - | Work submitted to a task is now checked against what that task asks for. A judgement must include both a verdict and the reasoning behind it, and an annotation can only use the labels the task defines. Unfinished drafts can still be saved. Task owners can also choose how many people annotate each item (1–10) when they create a task, and see it on the task's Setup page. They can change it while the task is a draft; once the task is activated it's locked, so every item is counted against the same number. | Yes - story complete | Also completes story D8 subtask 2: the annotator count in the app (SCRUM-48 built only the API half).
2026-10-11 | W9 | Yi Geng | Jingwei Lin | OK | SCRUM-99 | 48 | https://github.com/USYD-CS-Capstone/hej/pull/48 | Feature | hej-api (backend) | E3 | An expert's decision is recorded as its own decision | E | P1 | - | When reviewers disagree about an answer, or one escalates it, an independent expert now decides on that answer: accept it, send it back, or reject it, with the decision recorded on its own. When an item ends up with several accepted answers, an expert picks the one the item releases, or rejects them all and the item is marked unresolved. | No - more work to come | Co-reviewer: Hanchen Wang. Also relates to D1.
2026-10-11 | W9 | Yi Geng | Jingwei Lin | OK | SCRUM-100 | 48 | https://github.com/USYD-CS-Capstone/hej/pull/48 | Feature | hej-web (frontend) | E4 | Resolving a dispute doesn't erase the disagreement | E | P1 | - | A settled dispute keeps its whole story: who disagreed, the answer in question, and who decided it, how and why. An item nobody could settle is marked unresolved and releases no answer, instead of being forced to pick one. | Yes - story complete | Co-reviewer: Hanchen Wang.
2026-10-11 | W9 | Yi Geng | Jingwei Lin | OK | SCRUM-101 | 48 | https://github.com/USYD-CS-Capstone/hej/pull/48 | Feature | hej-api (backend) | E1 | Disagreement is noticed without anyone reporting it | E | P0 | - | When two reviewers reach different verdicts on the same answer, the platform now opens a dispute by itself if the project's policy says so, or flags the item for a manual look. Nobody has to notice and report it. | Yes - story complete | Co-reviewer: Hanchen Wang.
2026-10-11 | W9 | Hanchen Wang | Jingwei Lin | OK | SCRUM-70 | 51 | https://github.com/USYD-CS-Capstone/hej/pull/51 | Tests | Other | I2 | The platform is tested against cases designed to break it | I | P0 | - | The evaluation casebook now names the brief's seven adversarial categories and holds at least one test case for each, with gold-labelled records to check answers against. | No - more work to come
2026-10-11 | W9 | Hanchen Wang | Jingwei Lin | OK | SCRUM-69 | 62 | https://github.com/USYD-CS-Capstone/hej/pull/62 | Tests | CI / tooling | I1 | I can re-run the whole workflow against known cases | I | P0 | - | The scripted workflow cases can now be run again and again with the same result, and each run is compared case by case with an agreed baseline. A case that starts failing, stops running or disappears fails the build, so a regression is caught before it is merged. | Yes - story complete
2026-10-11 | W9 | Michael Max | Parth | OK | SCRUM-53 | 63 | https://github.com/USYD-CS-Capstone/hej/pull/63 | Feature | hej-api (backend) | F2 | Annotations remember which guideline they followed | F | P1 | - | Guidelines and project policies are now versioned: changing one adds a new version and never rewrites an old one. Every answer records the guideline, source and policy versions it was submitted under, so a policy can be changed mid-project without changing history. | Yes - story complete
2026-10-11 | W9 | Jingwei Lin | Hanchen Wang | OK | SCRUM-103 | 64 | https://github.com/USYD-CS-Capstone/hej/pull/64 | Feature | hej-web (frontend) | E6 | The dispute and arbitration screens show my real cases | E | P0 | 15 | The project's Disputes tab now lists the real disputes and reconciliations from every task, a page at a time, only for people allowed to read them. Annotators no longer see them. Each case has its own page inside its task, where an expert sees the evidence and the reviewer's proposed correction, and decides. Only someone allowed to decide is offered the decision. The item's work panel and the task history link to the case. The three dead placeholder pages are removed. | Yes - story complete
2026-10-12 | W9 | Kanishka Kathait | Jingwei Lin | OK | SCRUM-102 | 65 | https://github.com/USYD-CS-Capstone/hej/pull/65 | Feature | hej-api (backend) | H1 | A release is a fixed thing I can point at | H | P0 | - | A release now freezes the authoritative results at the time it is created, so later changes cannot alter the released artefact. | Yes - story complete
2026-10-13 | W9 | Dishank Aswal | Jingwei Lin | OK | SCRUM-37 | 66 | https://github.com/USYD-CS-Capstone/hej/pull/66 | Defect fix | hej-api (backend) | H4 | Every released item has exactly one authoritative answer | H | P0 | 4 | Each released or exported item now carries exactly one authoritative answer. Every other version is kept as superseded history, and an item an expert resolved as ambiguous is still exported, saying why it has no answer. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-12 | W9 | Jingwei Lin | Yi Geng | OK | SCRUM-123 | 67 | https://github.com/USYD-CS-Capstone/hej/pull/67 | Feature | hej-api (backend) | A3 | I can get a working copy of the platform running by myself | A | P0 | - | The demo setup now creates eleven named people instead of five "Test" accounts, with some people holding two roles (for example someone who annotates and also reviews). It also creates five ready-made test projects, one for each review policy, with work already set up at every stage, so the team can try reviews, disputes, reconciliations and sampled second reviews straight away instead of building them by hand. The top of every page now shows what you can do where you are: inside a project, what your roles let you do in that organisation; outside, a list for each organisation you belong to. | Yes - story complete | Backend and frontend: the seed, the login's per-organisation actions, and the header (web + packages/ui).
2026-10-13 | W9 | Jingwei Lin | Parth | OK | SCRUM-40 | 68 | https://github.com/USYD-CS-Capstone/hej/pull/68 | Defect fix | hej-api (backend) | F4 | History tells me who really did what | F | P1 | 21 | Each task's history now says who really did each step: a person, the AI model, or the platform itself. The AI's first answer shows as the model's, on behalf of whoever started the run, instead of looking like a person's answer. When the platform opens a dispute or a reconciliation by itself, that step gets its own entry, on behalf of the person whose decision led to it. History can also be read as people's decisions only. Separately, uploading a dataset with long item names no longer fails: a history entry can never stop the action it records. | Yes - story complete
2026-10-14 | W9 | Yi Geng | Hanchen Wang | OK | SCRUM-122 | 69 | https://github.com/USYD-CS-Capstone/hej/pull/69 | Feature | hej-api (backend) | E2 | I can send an item back to the annotator | E | P0 |  | When a reviewer returns or rejects the AI's first answer, the item now goes to a person instead of being stuck. A return shows them the AI's answer and the reason; a reject lets them start fresh. The AI is not asked again, and its answer stays in the record. | Yes - story complete | Ticket corrected from SCRUM-69 to SCRUM-122, as PR #69's title and branch say (Hanchen, 19 Oct). Also changes hej-web. What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-14 | W9 | Parth | Jingwei Lin | OK | SCRUM-98 | 70 | https://github.com/USYD-CS-Capstone/hej/pull/70 | Feature | hej-api (backend) | F1 | I can ask how any label came to exist | F | P0 |  | Every step in a label's life (the source, each AI or human answer, reviews, corrections, disputes, decisions and reopens) is now recorded as an event saying who did it and when, written at the moment it happens and never edited. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-14 | W9 | Jingwei Lin | Hanchen Wang | OK | SCRUM-71 | 71 | https://github.com/USYD-CS-Capstone/hej/pull/71 | Tests | CI / tooling | I2 | The platform is tested against cases designed to break it | I | P0 | 10, 16, 20, 29 | The evaluation casebook grew from 13 to 57 test cases. 48 of them run on every code change; the rest are written and wait for features still being built. Every kind of hard case the brief names now has a case, including annotators who disagree and a source that changes, which were missing before. Every defect fixed since the code audit now has a case that fails if it comes back. One case follows a real AG News record from upload through review, a blind second review, a dispute and the expert's decision to export. Writing the cases also found and fixed one bug: a reviewer's correction to a plainly labelled answer didn't change the label. | No - more work to come | Also fixes a platform bug in hej-api (review corrections).
2026-10-15 | W10 | Jingwei Lin | Hanchen Wang | OK | SCRUM-73 | 73 | https://github.com/USYD-CS-Capstone/hej/pull/73 | Feature | hej-api (backend) | I4 | I can see what AI assistance does to human judgement | I | P1 | - | Judgement tasks can now run the blind-then-reveal evaluation protocol the client described: each annotator records their own verdict first, then sees the AI's suggestion, then gives their final answer, and both answers are kept. The AI's suggestion stays hidden from every screen and API read until that annotator has committed their own verdict. The platform now measures what the AI does to people's answers: how often they kept their verdict or switched to the AI's, how their confidence changed, time spent before and after seeing the AI, and review burden. Against reference labels, the evaluation tools also measure anchoring, automation bias and whether answers got more or less correct. A judgement's verdict must now be one of the task's own labels. | Yes - story complete | Also changes hej-web (the work panel's three steps) and the evaluation harness. ADR 016. Client issue #72's gap 1 (guideline and policy provenance per stage) moves to SCRUM-72 as a follow-up.
2026-10-15 | W9 | Tim Chung | Hanchen Wang | OK | SCRUM-89 | 74 | https://github.com/USYD-CS-Capstone/hej/pull/74 | Feature | hej-api (backend) | J2 | I can see how my project is going at a glance | J | P2 |  | The existing project overview now shows project status, task counts by lifecycle state, and item counts by raw workflow status. It shows export progress using canonicalized-only counts, so the overview, task screen, and export panel agree. A permission-protected project endpoint supplies raw counts, and refresh handling keeps the workspace usable when counts are unavailable or a refresh fails. | Yes - story complete
2026-10-16 | W10 | Jingwei Lin |  | IN-PROCESS | SCRUM-88 | 75 | https://github.com/USYD-CS-Capstone/hej/pull/75 | Defect fix | hej-api (backend) | J1 | My organisation has a stable identity | J | P2 | - | Each organisation now opens at one address that never changes, and renaming an organisation is actually saved. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-16 | W10 | Yi Geng | Hanchen Wang | OK | SCRUM-118 | 76 | https://github.com/USYD-CS-Capstone/hej/pull/76 | Feature | hej-api (backend) | G2 | My project's governance posture actually governs | G | P1 |  | Projects that use the Expert Gate now hold every reviewed answer until an independent expert confirms it, and no AI answer can become final unless a person has reviewed it. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-16 | W10 | Jingwei Lin |  | IN-PROCESS | SCRUM-72 | 77 | https://github.com/USYD-CS-Capstone/hej/pull/77 | Feature | hej-api (backend) | I3 | I can tell whether reviewers actually agree | I | P1 | - | The platform now measures how far people agree with recognised statistics instead of a raw match rate: between the two reviewers who independently check a sampled answer, and between the annotators of the same item, for each task and side by side for the whole project on its Overview. It also measures the AI model itself, from a recorded run over the client's own data: on AG News llama3 was right 84.5% of the time and its confidence could be trusted; on Civil Comments it was right 65.5% of the time and overconfident, often calling toxic comments harmless while saying it was at least 80% sure. Each stage of the blind-then-reveal protocol (the AI's suggestion, the person's own verdict, and the moment the suggestion is shown) is now on the item's provenance record. | Yes - story complete
|  | Dishank Aswal | Yi Geng | OK | SCRUM-124 | 78 | https://github.com/USYD-CS-Capstone/hej/pull/78 | Feature | hej-api (backend) | D3 | The correction I make is the answer that gets saved | D | P0 |  | Reviewers’ corrections can now be accepted by an independent expert and become the authoritative answer. The original answer is retained as history, and reopening clears the correction’s authority., Experts can now choose “Accept reviewer’s correction” on a dispute case. The system records the exact accepted version, decision maker, justification, and dispute trail for auditability. | Yes - story complete
2026-10-16 | W10 | Jingwei Lin |  | IN-PROCESS | SCRUM-74 | 79 | https://github.com/USYD-CS-Capstone/hej/pull/79 | Tests | CI / tooling | I5 | I can prove the platform's records hold up | I | P1 | - | Two new checks read the platform's records after the fact and report anything that shouldn't be there, naming the task and item: a step taken by someone who didn't hold the right role at the time, or who judged their own work; and a released item whose history is missing a step or names the wrong person. They run on every code change against deliberately tampered test data, which they catch, and anyone can point them at a real database without changing it. | No - more work to come
2026-10-17 | W10 | Jingwei Lin |  | IN-PROCESS | SCRUM-45 | 80 | https://github.com/USYD-CS-Capstone/hej/pull/80 | Feature | hej-api (backend) | J4 | I can maintain a project after creating it | J | P2 | - | A project manager can now rename a project, change its description and how it is governed, and see every change in the project's history with who made it and what it was before. A project whose work is all finished can be archived: it stays readable, but nothing in it can be changed until it is restored, and the platform enforces this for every action, not only on screen. A project with unfinished work can't be archived, and the platform names the tasks still open. | No - more work to come
2026-10-19 | W10 | Michael Max | Hanchen Wang | OK | SCRUM-105 | 83 | https://github.com/USYD-CS-Capstone/hej/pull/83 | Feature | hej-api (backend) | H3 | A release that shouldn't exist is refused | H | P0 |  | A release is now refused before it is created if any item is unreviewed, disputed, superseded or missing its history, and the refusal names each item and the reason. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-19 | W10 | Michael Max | Hanchen Wang | OK | SCRUM-104 | 84 | https://github.com/USYD-CS-Capstone/hej/pull/84 | Feature | hej-api (backend) | H2 | Every release explains what's in it | H | P0 |  | Every release now comes with a manifest listing its items, how each was resolved, the versions it followed and where to find each item's history, so anyone can check the release with SHA-256 alone. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-19 | W10 | Yi Geng | Jingwei Lin | OK | SCRUM-107 | 81 | https://github.com/USYD-CS-Capstone/hej/pull/81 | Feature | hej-api (backend) | E5 | Escalation matches the assurance my project needs | E | P1 |  | The project's escalation posture is now shown on each task and item, and tests confirm that under every posture a dispute can only be closed by an independent expert. | Yes - story complete | What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-19 | W10 | Yi Geng |  | IN-PROCESS | SCRUM-106 | 85 | https://github.com/USYD-CS-Capstone/hej/pull/85 | Feature | hej-web (frontend) | F5 | I can see an item's whole story on one screen | F | P1 |  | A finalised item's whole production history can now be seen on one screen, as a graph from the source record through each answer, review and decision to the final answer and any release. | Yes - story complete | Row added by Hanchen, 19 Oct (PR opened that day). What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.
2026-10-19 | W10 | Yi Geng |  | IN-PROCESS | SCRUM-108 | 86 | https://github.com/USYD-CS-Capstone/hej/pull/86 | Feature | hej-web (frontend) | H6 | The export, policy and history screens show real data | H | P0 |  | A task's releases are now listed on its Finalized page, where a task owner can create one, open it, download it and check it against its recorded fingerprint. The manifest and the gate's messages are still to come. | No - more work to come | Row added by Hanchen, 19 Oct. Draft PR, stacked on #85. What changed drafted from the PR description by Hanchen, 19 Oct; the member may reword it.

## Dashboard
Dashboard
Everything here is calculated from the Contribution Log. Nothing on this tab needs to be typed.
PRS MERGED |  |  | STORIES TOUCHED |  |  | STORIES COMPLETE |  |  | SELF-REVIEWS
80 |  |  | 47 |  |  | 36 |  |  | 1
Contribution by member
Member | PRs merged | PRs reviewed | Features | Defect fixes | Tests / docs | Stories completed | First merge | Last merge | Share of PRs
Michael Max | 13 | 3 | 7 | 3 | 1 | 4 | 2026-09-12 | 2026-10-19 | 16.25%
Parth | 8 | 4 | 5 | 1 | 0 | 4 | 2026-09-14 | 2026-10-14 | 10%
Jingwei Lin | 23 | 21 | 12 | 8 | 3 | 10 | 2026-09-07 | 2026-10-17 | 28.75%
Hanchen Wang | 11 | 28 | 3 | 4 | 2 | 6 | 2026-09-07 | 2026-10-11 | 13.75%
Yi Geng | 10 | 10 | 6 | 1 | 0 | 5 | 2026-08-28 | 2026-10-16 | 12.5%
Dishank Aswal | 7 | 5 | 1 | 5 | 0 | 4 | 0 | 2026-10-13 | 8.75%
Kanishka Kathait | 4 | 3 | 3 | 1 | 0 | 2 | 2026-09-12 | 2026-10-12 | 5%
Tim Chung | 4 | 0 | 4 | 0 | 0 | 2 | 2026-09-14 | 2026-10-15 | 5%
TOTAL | 80 | 74 | 41 | 23 | 6 | 36
TOTAL counts distinct stories, so it can be lower than the column above if two people finished the same story.
PRs merged per week | [5 empty] | Weeks are calculated from the date merged. Blank weeks simply have nothing logged yet.
Week | Michael Max | Parth | Jingwei Lin | Hanchen Wang | Yi Geng | Dishank Aswal | Kanishka Kathait | Tim Chung | Total
W1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W6 | 3 | 0 | 3 | 2 | 0 | 2 | 1 | 0 | 11
W7 | 4 | 4 | 1 | 2 | 2 | 1 | 0 | 2 | 16
W8 | 2 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 12
Break | 1 | 3 | 6 | 2 | 0 | 1 | 1 | 1 | 15
W9 | 1 | 1 | 5 | 2 | 4 | 1 | 1 | 1 | 16
W10 | 2 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 8
W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Where the work went | [5 empty] | Review health
Area / repo | PRs |  | Work type | PRs
hej-web (frontend) | 15 |  | Feature | 41 |  | PRs with a named reviewer | 73
hej-api (backend) | 45 |  | Defect fix | 23 |  | PRs reviewed by their own author | 1
packages/ui | 0 |  | Refactor | 2 |  | Rows with no reviewer recorded | 6
labeling_ai_assistnat_mvp (AI) | 2 |  | Tests | 5 |  | Rows with no story linked | 6
Database / schema | 2 |  | Documentation | 1 |  | Rows missing a plain-English summary | 7
CI / tooling | 5 |  | Spike / Research | 1
Docs / report | 1 |  | DevOps / CI | 2
Other | 4 |  | Client / PM / Report | 0

## Jira Statistics
Jira Statistics
The CS-57 board, matched to the 59 committed backlog stories. Status and assignees are a snapshot of docs/Jira.csv; PR counts are live from the Contribution Log. Only the nine Owner cells are typed.
WORK ITEMS |  | IN PROGRESS |  | IN REVIEW |  | DONE |  | IN SPRINT W10 |  | UNASSIGNED
93 |  | 5 |  | 5 |  | 83 |  | 17 |  | 11
Work bundles | [5 empty] | Fill in the nine Owner cells once. This is the only typing on this tab.
# | Work bundle | What it covers |  | Stories | To do | Doing | Done | PRs
1 | AI task queue | Task queue with progress bar; completed / failed / retry |  | 1 | 0 | 0 | 1 | 7
2 | AI provider & failures | Annotation failure and the fake bounding-box fallback; integrate labeling_ai_assistnat_mvp |  | 1 | 0 | 0 | 1 | 1
3 | Project setup & status UI | Project / policy / task update, dataset upload, status page |  | 8 | 2 | 1 | 5 | 8
4 | Task & item backend | Illegal item status, cross-project writes, non-transactional task registration, missing transition out of draft, task-item routes and services |  | 5 | 0 | 0 | 5 | 6
5 | Annotation page & judgement | Annotation page with judgement feedback or justification |  | 7 | 0 | 2 | 5 | 12
6 | Draft ownership & verdict | Finalised annotation overwrite, draft ownership, judgement verdict and feedback |  | 3 | 0 | 0 | 3 | 5
7 | Review, permissions & dispute | Reviewer correction, avoid self-review, review action, permission and dispute |  | 9 | 1 | 2 | 6 | 11
8 | Audit & history | Audit and history |  | 4 | 0 | 2 | 2 | 4
9 | Release & export | Release and export |  | 5 | 2 | 2 | 1 | 1
- | Unallocated | Not in the allocation document. Assign these before they become a surprise. |  | 20 | 5 | 5 | 4 | 16
Committed scope | [5 empty] | Done counts what the board says is done. A story with no ticket cannot be done. | By epic
Priority | Stories | Done | Doing | On board | % done |  | Epic | Stories | Done
P0 - committed core | 35 | 21 | 8 | 32 | 60% |  | A - Trustworthy Foundations | 6 | 2
P1 | 23 | 10 | 5 | 20 | 43.48% |  | B - Setting Up Work | 8 | 7
P2 - nice to have | 5 | 2 | 1 | 5 | 40% |  | C - AI-Assisted First Pass | 5 | 5
All stories | 63 | 33 | 14 | 57 | 52.38% |  | D - Review & Cross-Validation | 9 | 8
[7 empty] | E - Disagreement & Dispute | 6 | 3
[7 empty] | F - Provenance & History | 5 | 1
[7 empty] | G - Roles, Permissions & Organisations | 5 | 4
[7 empty] | H - Release & Export | 6 | 1
[7 empty] | I - Evaluation | 5 | 1
[7 empty] | J - Organisations & Dashboard | 4 | 1
[7 empty] | K - Evidence & Handover | 4 | 0
Waiting for a ticket | [5 empty] | Committed stories with nothing on the board. Nobody is working on these, because there is nothing to pick up.
None | Every committed story that is not dropped has at least one ticket on the board.
Dropped | 6 stories the team dropped, so no ticket is expected: A1 A5 K1 K2 K3 K4
Workload by person | [5 empty] | Issues assigned on the board, beside PRs actually logged. Both count the same eight people.
Member | Assigned | To do | Doing | In review | Done | In sprint | Bundles touched | PRs logged | Reviews
Michael Max | 10 | 0 | 0 | 0 | 10 | 2 | AI task queue, AI provider & failures, Unallocated, Release & export | 13 | 3
Parth | 8 | 0 | 1 | 0 | 7 | 1 | Annotation page & judgement, Review, permissions & dispute, AI task queue, Audit & history, Unallocated, Release & export | 8 | 4
Jingwei Lin | 24 | 0 | 1 | 3 | 20 | 6 | Project setup & status UI, Task & item backend, Draft ownership & verdict, Review, permissions & dispute, Audit & history, Unallocated, Annotation page & judgement | 23 | 21
Hanchen Wang | 10 | 0 | 0 | 0 | 10 | 0 | Draft ownership & verdict, Audit & history, Unallocated, Annotation page & judgement | 11 | 28
Yi Geng | 13 | 0 | 0 | 2 | 11 | 4 | Unallocated, Review, permissions & dispute, Task & item backend, Project setup & status UI, Annotation page & judgement | 10 | 10
Dishank Aswal | 7 | 0 | 0 | 0 | 7 | 1 | Task & item backend, Release & export, Audit & history, Annotation page & judgement, Review, permissions & dispute | 7 | 5
Kanishka Kathait | 5 | 0 | 1 | 0 | 4 | 1 | Task & item backend, Annotation page & judgement, Unallocated, Release & export | 4 | 3
Tim Chung | 5 | 0 | 1 | 0 | 4 | 1 | Project setup & status UI, Unallocated | 4 | 0
Nobody assigned | 11 | 11 of 93 issues on the board have no owner.
Every issue on the board
Issue | Type | Status | Assignee | Sprint | Jira epic | Summary | Backlog story | Matched from | PRs
SCRUM-1 | Task | Done | Michael Max | W7 Lock down review data | AI Annotation Pipeline | Task queue: Create AI batch job and per-item job status models | C2 | description | 1
SCRUM-2 | Task | Done | Michael Max | W7 Lock down review data | AI Annotation Pipeline | Task queue: Execute task annotation asynchronously through a worker | C2 | description | 2
SCRUM-3 | Task | Done | Michael Max | W8 Route work, record decision | AI Annotation Pipeline | Task queue: Retry failed items and preserve permanent failures | C2 | description | 1
SCRUM-5 | Task | Done | Michael Max | Mid-semester Break | AI Annotation Pipeline | Task queue: Display batch progress and per-item job status | C2 | description | 1
SCRUM-6 | Task | Done | Yi Geng | W7 Lock down review data | Annotation & Human Judgement | AI-Provider: Integrate labeling_ai_assistnat_mvp as an AI provider | C1 | description | 2
SCRUM-7 | Task | Done | Michael Max | W6 Governance & data-integrity | Annotation & Human Judgement | AI-Provider: Stop generating fake annotations when the AI provider fails | C3 | description | 0
SCRUM-8 | Task | Done | Tim Chung | W7 Lock down review data | Organisation Management | Organisation management: Invitation & acceptance | G5 | description | 1
SCRUM-20 | Task | Done | Jingwei Lin | W7 Lock down review data | Project, Policy & Task Lifecycle | Project & Policy: Configure project review and annotation policies | B2 | description | 1
SCRUM-21 | Task | Done | Jingwei Lin | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Prevent cross-project task and task-item writes | G3 | description | 1
SCRUM-22 | Task | Done | Dishank Aswal | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Validate task-item status before database commit | G4 | description | 1
SCRUM-23 | Task | Done | Dishank Aswal | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Preserve lifecycle conflict responses as HTTP 409 | B5 | description | 1
SCRUM-24 | Task | Done | Dishank Aswal | W8 Route work, record decision | Project, Policy & Task Lifecycle | Task Lifecycle: Implement valid task lifecycle transitions | B4 | description | 1
SCRUM-25 | Task | Done | Hanchen Wang | W6 Governance & data-integrity | Annotation & Human Judgement | Annotation: Enforce draft ownership | D6 | description | 1
SCRUM-26 | Task | Done | Hanchen Wang | W7 Lock down review data | Annotation & Human Judgement | Annotation: Make draft submission and annotation creation atomic | D5 | description | 1
SCRUM-27 | Task | Done | Jingwei Lin | W7 Lock down review data | Review, Dispute & Adjudication | Review / Annotation: Reviewer should be able to select the correct submitted annotation | D4 | description | 1
SCRUM-28 | Task | Done | Hanchen Wang | W7 Lock down review data | Annotation & Human Judgement | Annotation: Preventing finalized annotations from being overwritten | D5 | description | 1
SCRUM-29 | Task | Done | Jingwei Lin | W6 Governance & data-integrity | Review, Dispute & Adjudication | Review: Retire or restrict legacy review mutation endpoints | D2 | description | 1
SCRUM-30 | Task | Done | Michael Max | W6 Governance & data-integrity | Annotation & Human Judgement | AI-Provider: Store & Display AI suggestions, failures and unavailable states | C3 | description | 1
SCRUM-31 | Task | Done | Parth | W6 Governance & data-integrity | Review, Dispute & Adjudication | Review: Record verdict, feedback & justification | C5 | description | 1
SCRUM-32 | Task | Done | Jingwei Lin | Mid-semester Break | Review, Dispute & Adjudication | Review: Persist reviewer corrections as structured data | D3 | description | 1
SCRUM-34 | Task | Done | Kanishka Kathait | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Make dataset registration transactional | B5 | description | 1
SCRUM-35 | Task | Done | Parth | W6 Governance & data-integrity | Review, Dispute & Adjudication | Dispute / Annotation: Implement "Dispute & send back to annotator" | E2 | description | 1
SCRUM-37 | Task | Done | Dishank Aswal | W9 Trace decisions, settle on | Provenance & Audit History | Provenance: Guarantee one canonical answer per task item | H4 | description
SCRUM-38 | Task | Done | Hanchen Wang | Mid-semester Break | Provenance & Audit History | Provenance: Preserve AI, annotator, reviewer and adjudicator outputs separately | F3 | description | 1
SCRUM-40 | Task | Done | Jingwei Lin | W9 Trace decisions, settle on | Provenance & Audit History | Provenance: Record correct audit actor types | F4 | description
SCRUM-41 | Task | Done | Jingwei Lin | Mid-semester Break | Provenance & Audit History | Provenance: Remove duplicate escalation audit changes | F4 | description | 1
SCRUM-43 | Task | Done | Dishank Aswal | W7 Lock down review data | Dataset Release & Export | Release & Export: Align task completion and export readiness | B6, H5 | description | 1
SCRUM-44 | Task | Done | Jingwei Lin | W6 Governance & data-integrity | Organisation Management | Organisation Management: Users can only perform actions that are permitted by their roles. | G1 | backlog CSV | 1
SCRUM-45 | Task | In Review | Jingwei Lin | W10 Gate releases, prove them | Project, Policy & Task Lifecycle | Project lifecycle: Update and archive a project | J4 | description
SCRUM-46 | Task | Done | Michael Max | W8 Route work, record decision | AI Annotation Pipeline | Task queue: Trigger an AI run and route completed items to review | C2 | description | 1
SCRUM-47 | Task | Done |  |  | Annotation & Human Judgement | Annotation: Connect the existing text annotation page to live APIs |  |  | 0
SCRUM-48 | Task | Done | Kanishka Kathait | W7 Lock down review data | Review, Dispute & Adjudication | Work queues: role-checked queues, annotator count and submission limit (API) | D8 | description | 2
SCRUM-49 | Task | Done |  | W9 Trace decisions, settle on | Review, Dispute & Adjudication | Review: Execute accept, adjust, reject and dispute transitions | C5, D3, E1 | backlog CSV | 0
SCRUM-50 | Task | Done | Jingwei Lin | W8 Route work, record decision | Project, Policy & Task Lifecycle | Policy: Resolve project policy into executable task rules | B2, G2 | description | 1
SCRUM-51 | Task | Done | Parth | W8 Route work, record decision | Review, Dispute & Adjudication | Review: Independent second reviewer | D7, E1 | description | 1
SCRUM-52 | Task | Done | Parth | Mid-semester Break | Review, Dispute & Adjudication | Dispute: Adjudicator queue and authorization | D8, E3, E6, G1 | description | 1
SCRUM-53 | Task | Done | Michael Max | W9 Trace decisions, settle on | Provenance & Audit History | Provenance: Version guidelines, sources and review policies | F2 | description
SCRUM-54 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Define the AnnotationAssistant interface | C1 | parent ticket | 0
SCRUM-55 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Replace the Gemini call with an OpenAI-compatible client | C1 | parent ticket | 0
SCRUM-56 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Port the MVP's four text tasks behind the interface | C1 | parent ticket | 0
SCRUM-68 | Task | Done | Jingwei Lin | W8 Route work, record decision | Evaluation Harness and Casebook | Evaluation1: Scenario harness that drives the workflow end to end | I1 | description | 1
SCRUM-69 | Task | Done | Hanchen Wang | W9 Trace decisions, settle on | Evaluation Harness and Casebook | Evaluation2: Repeatable runs and regression reporting | I1 | description | 2
SCRUM-70 | Task | Done | Hanchen Wang | W9 Trace decisions, settle on | Evaluation Harness and Casebook | Evaluation3: Casebook structure and the adversarial categories | I2 | description | 1
SCRUM-71 | Task | Done | Jingwei Lin | W9 Trace decisions, settle on | Evaluation Harness and Casebook | Evaluation4: Grow the casebook to 40–60 cases | I2 | description
SCRUM-72 | Task | Done | Jingwei Lin | W10 Gate releases, prove them | Evaluation Harness and Casebook | Evaluation5: Reviewer agreement and AI suggestion quality | I3 | description
SCRUM-73 | Task | Done | Jingwei Lin | W10 Gate releases, prove them | Evaluation Harness and Casebook | Evaluation6: Measure AI influence on human judgement, with blind-then-reveal | I4 | description
SCRUM-74 | Task | In Review | Jingwei Lin | W10 Gate releases, prove them | Evaluation Harness and Casebook | Evaluation7: Integrity checks on provenance, roles and releases | I5 | description
SCRUM-75 | Task | In Progress | Kanishka Kathait | W10 Gate releases, prove them | Evaluation Harness and Casebook | Evaluation8: Findings record including negative results | I5 | description
SCRUM-81 | Task | Done | Yi Geng | W6 Governance & data-integrity | Trustworthy Foundations | Schema: Fix db setup issues | A3 | backlog CSV | 2
SCRUM-82 | Task | Done | Hanchen Wang | W6 Governance & data-integrity | Trustworthy Foundations | Schema: Restore existing testcases | A2 | backlog CSV | 1
SCRUM-84 | Task | Done | Yi Geng | W6 Governance & data-integrity | Trustworthy Foundations | Schema: Replace hardcoded credentials | A4 | backlog CSV | 0
SCRUM-85 | Task | Done | Jingwei Lin | W9 Trace decisions, settle on | Project, Policy & Task Lifecycle | Task lifecycle: Create annotation and judgement tasks with a result shape | B3 | description | 1
SCRUM-86 | Task | Done |  | Mid-semester Break | Review, Dispute & Adjudication | Review: Prevent self-review of own annotations | D1 | description | 0
SCRUM-87 | Task | Done | Jingwei Lin | Mid-semester Break | Annotation & Human Judgement | AI assist: Human-only and AI-first task modes | C4 | description | 1
SCRUM-88 | Task | In Review | Jingwei Lin | W10 Gate releases, prove them | Organisation Management | Organisation Management: Stable organisation identifier and URL | J1 | description
SCRUM-89 | Task | Done | Tim Chung | W9 Trace decisions, settle on | Project, Policy & Task Lifecycle | Project: Overview of status and progress | J2 | description
SCRUM-90 | Task | Done | Tim Chung | W7 Lock down review data | Organisation Management | Organisation Management: Invite, remove and role-manage members | J3 | description | 1
SCRUM-91 | Task | In Progress | Tim Chung | W10 Gate releases, prove them | Project, Policy & Task Lifecycle | Project lifecycle: Create a project scoped to an organisation | B1 | description
SCRUM-92 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Update the annotation editing page to ensure that the output results of MVP can be compatible with the existing interface of Hej. | C1 | parent ticket | 0
SCRUM-93 | Task | Done | Kanishka Kathait | W8 Route work, record decision | Review, Dispute & Adjudication | Work queues: available-work list, progress and submission limit (WEB) | D8 | description | 1
SCRUM-94 | Task | Done | Parth | W7 Lock down review data | Trustworthy Foundations | Infrastructure: run on PostgreSQL while keeping SQLite working | C2 | description | 1
SCRUM-95 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Add definition settings to labels field | C1 | parent ticket | 0
SCRUM-96 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Enable label list file upload | C1 | parent ticket | 0
SCRUM-97 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | enable custom task with user-defined instructions, output-type and schema | C1 | parent ticket | 0
SCRUM-98 | Task | Done | Parth | W9 Trace decisions, settle on | Provenance & Audit History | Provenance: Record the production history of every label | F1 | description
SCRUM-99 | Task | Done | Yi Geng | Mid-semester Break | Review, Dispute & Adjudication | Dispute: Record an expert adjudication as its own decision | D1, E3 | description | 1
SCRUM-100 | Task | Done | Yi Geng | Mid-semester Break | Review, Dispute & Adjudication | Dispute: Keep the disagreement after the dispute is resolved | E4 | description | 1
SCRUM-101 | Task | Done | Yi Geng | W9 Trace decisions, settle on | Review, Dispute & Adjudication | Dispute: Detect reviewer disagreement automatically | E1 | description | 1
SCRUM-102 | Task | Done | Kanishka Kathait | W9 Trace decisions, settle on | Dataset Release & Export | Release: Create an immutable release artefact | H1 | description
SCRUM-103 | Task | Done | Jingwei Lin | W9 Trace decisions, settle on | Review, Dispute & Adjudication | Dispute: Connect the dispute and arbitration screens | E6 | description | 1
SCRUM-104 | Task | Done | Michael Max | W10 Gate releases, prove them | Dataset Release & Export | Release: Produce a manifest for every release | H2 | description
SCRUM-105 | Task | Done | Michael Max | W10 Gate releases, prove them | Dataset Release & Export | Release: Refuse a release that fails its pre-release checks | H3 | description
SCRUM-106 | Task | In Review | Yi Geng | W10 Gate releases, prove them | Provenance & Audit History | Provenance: Show an item's whole timeline on one screen | F5 | description
SCRUM-107 | Task | Done | Yi Geng | W10 Gate releases, prove them | Review, Dispute & Adjudication | Dispute: Make the escalation posture configurable and enforced | E5, G2 | description
SCRUM-108 | Task | In Review | Yi Geng | W10 Gate releases, prove them | Dataset Release & Export | Release: Show real releases, policy and history on the project screens | H6 | description
SCRUM-109 | Task | Done | Parth | W9 Trace decisions, settle on | Review, Dispute & Adjudication | Review: Review actions always move item status, and state cannot diverge from history | D2 | description | 1
SCRUM-110 | Task | Done | Jingwei Lin | Mid-semester Break | Annotation & Human Judgement | Review: Project owner reopens a finalised item | D9 | description | 1
SCRUM-111 | Task | Done | Yi Geng | W8 Route work, record decision | Project, Policy & Task Lifecycle | Task lifecycle: Import a JSONL dataset as one item per record | B7 | description | 1
SCRUM-112 | Task | Done | Yi Geng | W8 Route work, record decision | Project, Policy & Task Lifecycle | Task lifecycle: Choose the annotation surface per task (annotation_type) | B8 | description | 1
SCRUM-113 | Task | Done | Hanchen Wang | W8 Route work, record decision | Review, Dispute & Adjudication | Review: choose which submission to review on a multi-annotator item (WEB) | D4, D8 | description | 1
SCRUM-114 | Task | Done | Hanchen Wang | W8 Route work, record decision | Review, Dispute & Adjudication | Work queues: item workspace panel — independence, refusals and S10 (WEB) | D8 | description | 1
SCRUM-115 | Task | Done | Tim Chung | W8 Route work, record decision | Organisation Management | Organisation Management: Invitee accepts a pending invitation; role chosen at invitation | J3 | description | 1
SCRUM-116 | Task | Done | Jingwei Lin | Mid-semester Break | Review, Dispute & Adjudication | Review: refuse a decision on a submission that is not awaiting the reviewer | D1, D5, D8 | description | 1
SCRUM-117 | Task | Done | Dishank Aswal | Mid-semester Break | Review, Dispute & Adjudication | Review: an annotator resubmits only work that is theirs to redo | D8 | description | 1
SCRUM-118 | Task | Done | Yi Geng | W10 Gate releases, prove them | Project, Policy & Task Lifecycle | Governance: Make the project's governance posture govern canonicalisation | G2 | description
SCRUM-119 | Task | Done | Hanchen Wang | Mid-semester Break | Trustworthy Foundations | Performance: Read a task's drafts in one request | A6 | description | 1
SCRUM-120 | Task | Done | Jingwei Lin | Mid-semester Break | Annotation & Human Judgement | Bug: A reopened item is flipped to expert send-back by the next read | D9 | description | 1
SCRUM-121 | Task | In Progress |  | W10 Gate releases, prove them | Trustworthy Foundations | Performance: Reads never write, and the project page counts its tasks once | A6 | description
SCRUM-122 | Task | Done | Yi Geng | W9 Trace decisions, settle on | Review, Dispute & Adjudication | Review: a returned or rejected AI first pass goes to a human annotator | E2 | description
SCRUM-123 | Task | Done | Jingwei Lin | W9 Trace decisions, settle on | Trustworthy Foundations | Seed a cast of named people and a test project for every feature | A3 | description
SCRUM-124 | Task | Done | Dishank Aswal | W10 Gate releases, prove them | Review, Dispute & Adjudication | Dispute: An expert can accept a reviewer's correction as the answer | D3, E3 | description
SCRUM-125 | Task | In Progress | Parth | W10 Gate releases, prove them | Trustworthy Foundations | Hardening: close the gaps no ticket covers — export figure check, CI, compose secrets and explicit-ID locking | A1, A4, H5 | description
SCRUM-126 | Task | In Progress | Jingwei Lin | W10 Gate releases, prove them | Review, Dispute & Adjudication | Dispute: An independent reviewer can settle a held disagreement, except where adjudication is mandatory | E5, G2 | description

## Client Report
Client Report
Set the two dates below. Everything else recalculates for that period - ready to paste into the Status Checking form or the weekly client meeting.
Reporting period starts | 2026-08-27 | <- type the two dates here
Reporting period ends | 2026-10-28
This period at a glance |  |  | Delivery by epic, this period
PRs merged | 79 |  | Epic | PRs | Stories done
Members who merged | 8 |  | A - Trustworthy Foundations | 5 | 2
Stories completed | 35 |  | B - Setting Up Work | 8 | 6
Defect-fix PRs | 23 |  | C - AI-Assisted First Pass | 12 | 4
Feature PRs | 40 |  | D - Review & Cross-Validation | 18 | 7
PRs reviewed by a second person | 73 |  | E - Disagreement & Dispute | 5 | 4
|  |  | F - Provenance & History | 4 | 3
|  |  | G - Roles, Permissions & Organisations | 5 | 4
|  |  | H - Release & Export | 1 | 1
Individual contribution, this period |  |  | I - Evaluation | 7 | 3
Member | PRs | Reviews given | Stories involved
Michael Max | 13 | 3 | 5
Parth | 8 | 4 | 6
Jingwei Lin | 23 | 21 | 21
Hanchen Wang | 11 | 28 | 9
Yi Geng | 10 | 10 | 6
Dishank Aswal | 6 | 5 | 5
Kanishka Kathait | 4 | 3 | 3
Tim Chung | 4 | 0 | 3

## Lists
Members | Week 1 Monday | Work type | Area / repo | Story complete? | Epic | Story ID | Epic | Priority | Role | Story title | SCRUM ticket(s) | Week | Starts | Ends | Work bundle | Jira status | SCRUM ticket
Michael Max | 2026-08-03 | Feature | hej-web (frontend) | Yes - story complete | A | - |  |  |  | (not tied to a backlog story) |  | W1 | 2026-08-03 | 2026-08-09 |  |  | SCRUM-1
Parth | Check this date once, then leave it alone. | Defect fix | hej-api (backend) | No - more work to come | B | A1 | A | P0 | Lead | Changes are reviewed before they reach the platform | SCRUM-125 | W2 | 2026-08-10 | 2026-08-16 | Unallocated | Dropped | SCRUM-2
Jingwei Lin | Every Week number is counted from here. | Refactor | packages/ui | N/A - not story work | C | A2 | A | P0 | SC | I can trust that a fix in one place hasn't broken another | SCRUM-82 | W3 | 2026-08-17 | 2026-08-23 | Unallocated | Done | SCRUM-3
Hanchen Wang | To check it: look at the week calendar in columns T-V. | Tests | labeling_ai_assistnat_mvp (AI) |  | D | A3 | A | P0 | SC | I can get a working copy of the platform running by myself | SCRUM-81, SCRUM-123 | W4 | 2026-08-24 | 2026-08-30 | Unallocated | Done | SCRUM-5
Yi Geng | W6 should read Mon 7 Sep 2026, and W12 should be the last week. The mid-semester break (28 Sep) is its own week, Break. | Documentation | Database / schema |  | E | A4 | A | P0 | SC | Platform credentials aren't sitting in shared code | SCRUM-84, SCRUM-125 | W5 | 2026-08-31 | 2026-09-06 | Unallocated | In progress | SCRUM-6
Dishank Aswal |  | Spike / Research | CI / tooling |  | F | A5 | A | P0 | SC | A status means the same thing wherever I see it |  | W6 | 2026-09-07 | 2026-09-13 | Unallocated | Dropped | SCRUM-7
Kanishka Kathait |  | DevOps / CI | Docs / report |  | G | B1 | B | P0 | BE/FE | I can create a project to hold related work | SCRUM-91 | W7 | 2026-09-14 | 2026-09-23 | Project setup & status UI | In progress | SCRUM-8
Tim Chung |  | Client / PM / Report | Other |  | H | B2 | B | P0 | BE | I can decide how carefully my project's work gets reviewed | SCRUM-20, SCRUM-50 | W8 | 2026-09-24 | 2026-09-30 | Project setup & status UI | Done | SCRUM-20
[5 empty] | I | B3 | B | P0 | BE/FE | I can create a task for a specific piece of work | SCRUM-85 | Break | 2026-10-01 | 2026-10-07 | Project setup & status UI | Done | SCRUM-21
[5 empty] | J | B4 | B | P0 | BE | My task moves through real states, not just “draft” | SCRUM-24 | W9 | 2026-10-08 | 2026-10-14 | Task & item backend | Done | SCRUM-22
[5 empty] | K | B5 | B | P0 | BE | Loading a dataset either works or leaves nothing behind | SCRUM-23, SCRUM-34 | W10 | 2026-10-15 | 2026-10-21 | Task & item backend | Done | SCRUM-23
[6 empty] | B6 | B | P1 | BE | “Done” means the same thing everywhere I look | SCRUM-43 | W11 | 2026-10-22 | 2026-10-28 | Audit & history | Done | SCRUM-24
[6 empty] | C1 | C | P1 | BE | The AI assistant can be swapped without disrupting my work | SCRUM-6 | W12 | 2026-10-29 | 2026-11-01 | Unallocated | Done | SCRUM-25
[6 empty] | C2 | C | P0 | BE | A large batch of items gets AI-annotated reliably | SCRUM-1, SCRUM-2, SCRUM-3, SCRUM-5, SCRUM-46, SCRUM-94 | End |  | 2026-11-01 | AI task queue | Done | SCRUM-26
[6 empty] | C3 | C | P0 | BE | I'm told when the AI failed instead of being shown a fake answer | SCRUM-7, SCRUM-30 | Project ends at the close of W12. |  |  | AI provider & failures | Done | SCRUM-27
[6 empty] | C4 | C | P1 | BE/FE | I can control whether reviewers see the AI's answer first | SCRUM-87 |  |  |  | Annotation page & judgement | Done | SCRUM-28
[6 empty] | C5 | C | P1 | BE/FE | I can record why I decided, not just what I decided | SCRUM-31, SCRUM-49 |  |  |  | Annotation page & judgement | Done | SCRUM-29
[6 empty] | D1 | D | P0 | BE | I can't approve my own work | SCRUM-86, SCRUM-99, SCRUM-116 |  |  |  | Review, permissions & dispute | Done | SCRUM-30
[6 empty] | D2 | D | P0 | BE | Approval history can't be rewritten behind my back | SCRUM-29, SCRUM-109 |  |  |  | Review, permissions & dispute | Done | SCRUM-31
[6 empty] | D3 | D | P0 | BE | The correction I make is the answer that gets saved | SCRUM-32, SCRUM-49, SCRUM-124 |  |  |  | Review, permissions & dispute | Done | SCRUM-32
[6 empty] | D4 | D | P0 | BE | I know I'm reviewing the right person's work | SCRUM-27, SCRUM-113 |  |  |  | Draft ownership & verdict | Done | SCRUM-34
[6 empty] | D5 | D | P0 | BE | Finalised means finalised | SCRUM-26, SCRUM-28, SCRUM-116 |  |  |  | Draft ownership & verdict | Done | SCRUM-35
[6 empty] | D6 | D | P0 | BE | My unfinished work is mine | SCRUM-25 |  |  |  | Draft ownership & verdict | Done | SCRUM-37
[6 empty] | D7 | D | P1 | BE | A defined share of items gets independently double-checked | SCRUM-51 |  |  |  | Annotation page & judgement | Done | SCRUM-38
[6 empty] | D8 | D | P0 | BE/FE | Work reaches the right person | SCRUM-48, SCRUM-52, SCRUM-93, SCRUM-113, SCRUM-114, SCRUM-116, SCRUM-117 |  |  |  | Annotation page & judgement | Done | SCRUM-40
[6 empty] | E1 | E | P0 | BE | Disagreement is noticed without anyone reporting it | SCRUM-49, SCRUM-51, SCRUM-101 |  |  |  | Review, permissions & dispute | Done | SCRUM-41
[6 empty] | E2 | E | P0 | FE | I can send an item back to the annotator | SCRUM-35, SCRUM-122 |  |  |  | Annotation page & judgement | Done | SCRUM-43
[6 empty] | E3 | E | P1 | BE | An expert's decision is recorded as its own decision | SCRUM-52, SCRUM-99, SCRUM-124 |  |  |  | Review, permissions & dispute | Done | SCRUM-44
[6 empty] | E4 | E | P1 | BE | Resolving a dispute doesn't erase the disagreement | SCRUM-100 |  |  |  | Review, permissions & dispute | Done | SCRUM-45
[6 empty] | E5 | E | P1 | BE | Escalation matches the assurance my project needs | SCRUM-107, SCRUM-126 |  |  |  | Review, permissions & dispute | In progress | SCRUM-46
[6 empty] | E6 | E | P0 | FE | The dispute and arbitration screens show my real cases | SCRUM-52, SCRUM-103 |  |  |  | Annotation page & judgement | Done | SCRUM-47
[6 empty] | F1 | F | P0 | BE | I can ask how any label came to exist | SCRUM-98 |  |  |  | Audit & history | Done | SCRUM-48
[6 empty] | F2 | F | P1 | BE | Annotations remember which guideline they followed | SCRUM-53 |  |  |  | Unallocated | Done | SCRUM-49
[6 empty] | F3 | F | P0 | BE | The AI's suggestion, the human's answer and the reviewer's correction stay separate | SCRUM-38 |  |  |  | Audit & history | Done | SCRUM-50
[6 empty] | F4 | F | P1 | BE | History tells me who really did what | SCRUM-40, SCRUM-41 |  |  |  | Audit & history | Done | SCRUM-51
[6 empty] | F5 | F | P1 | FE | I can see an item's whole story on one screen | SCRUM-106 |  |  |  | Unallocated | In progress | SCRUM-52
[6 empty] | G1 | G | P0 | BE | My role determines what I can do | SCRUM-44, SCRUM-52 |  |  |  | Review, permissions & dispute | Done | SCRUM-53
[6 empty] | G2 | G | P1 | BE | My project's governance posture actually governs | SCRUM-50, SCRUM-107, SCRUM-118, SCRUM-126 |  |  |  | Unallocated | In progress | SCRUM-54
[6 empty] | G3 | G | P0 | BE | My work stays inside my project | SCRUM-21 |  |  |  | Task & item backend | Done | SCRUM-55
[6 empty] | G4 | G | P1 | BE/SC | The platform refuses states that can't exist | SCRUM-22 |  |  |  | Task & item backend | Done | SCRUM-56
[6 empty] | G5 | G | P0 | BE | I can actually invite someone into my organisation | SCRUM-8 |  |  |  | Project setup & status UI | Done | SCRUM-68
[6 empty] | H1 | H | P0 | BE | A release is a fixed thing I can point at | SCRUM-102 |  |  |  | Release & export | Done | SCRUM-69
[6 empty] | H2 | H | P0 | BE | Every release explains what's in it | SCRUM-104 |  |  |  | Release & export | Done | SCRUM-70
[6 empty] | H3 | H | P0 | BE | A release that shouldn't exist is refused | SCRUM-105 |  |  |  | Release & export | Done | SCRUM-71
[6 empty] | H4 | H | P0 | BE | Every released item has exactly one authoritative answer | SCRUM-37 |  |  |  | Release & export | Done | SCRUM-72
[6 empty] | H5 | H | P1 | BE | Export figures agree with the rest of the platform | SCRUM-43, SCRUM-125 |  |  |  | Release & export | In progress | SCRUM-73
[6 empty] | H6 | H | P0 | FE | The export, policy and history screens show real data | SCRUM-108 |  |  |  | Unallocated | In progress | SCRUM-74
[6 empty] | I1 | I | P0 | GOV | I can re-run the whole workflow against known cases | SCRUM-68, SCRUM-69 |  |  |  | Unallocated | Done | SCRUM-75
[6 empty] | I2 | I | P0 | GOV | The platform is tested against cases designed to break it | SCRUM-70, SCRUM-71 |  |  |  | Unallocated | Done | SCRUM-81
[6 empty] | I3 | I | P1 | GOV | I can tell whether reviewers actually agree | SCRUM-72 |  |  |  | Unallocated | Done | SCRUM-82
[6 empty] | I4 | I | P1 | GOV | I can see what AI assistance does to human judgement | SCRUM-73 |  |  |  | Unallocated | Done | SCRUM-84
[6 empty] | I5 | I | P1 | GOV | I can prove the platform's records hold up | SCRUM-74, SCRUM-75 |  |  |  | Unallocated | In progress | SCRUM-85
[6 empty] | J1 | J | P2 | BE | My organisation has a stable identity | SCRUM-88 |  |  |  | Project setup & status UI | In progress | SCRUM-86
[6 empty] | J2 | J | P2 | FE | I can see how my project is going at a glance | SCRUM-89 |  |  |  | Unallocated | Done | SCRUM-87
[6 empty] | J3 | J | P2 | BE/FE | I can invite and manage my team | SCRUM-90, SCRUM-115 |  |  |  | Project setup & status UI | Done | SCRUM-88
[6 empty] | J4 | J | P2 | BE/FE | I can maintain a project after creating it | SCRUM-45 |  |  |  | Project setup & status UI | In progress | SCRUM-89
[6 empty] | K1 | K | P1 | Lead | A reader can understand the system without us in the room |  |  |  |  | Unallocated | Dropped | SCRUM-90
[6 empty] | K2 | K | P1 | all | Each of us can defend our own design decisions |  |  |  |  | Unallocated | Dropped | SCRUM-91
[6 empty] | K3 | K | P1 | GOV | What didn't work is recorded as carefully as what did |  |  |  |  | Unallocated | Dropped | SCRUM-92
[6 empty] | K4 | K | P0 | Lead | The end-to-end demonstration works when it matters |  |  |  |  | Unallocated | Dropped | SCRUM-93
[6 empty] | B7 | B | P1 | BE | Each record in my dataset becomes its own item | SCRUM-111 |  |  |  | Task & item backend | Done | SCRUM-94
[6 empty] | B8 | B | P2 | BE/FE | My task chooses how people annotate it, not a hard-coded subtype | SCRUM-112 |  |  |  | Project setup & status UI | Done | SCRUM-95
[6 empty] | D9 | D | P1 | BE/FE | The project owner can deliberately reopen a finalised item | SCRUM-110, SCRUM-120 |  |  |  | Review, permissions & dispute | Done | SCRUM-96
[6 empty] | A6 | A | P1 | BE/FE | A dataset-sized task opens without a wait | SCRUM-119, SCRUM-121 |  |  |  | Annotation page & judgement | In progress | SCRUM-97
SCRUM-98
SCRUM-99
SCRUM-100
SCRUM-101
SCRUM-102
SCRUM-103
SCRUM-104
SCRUM-105
SCRUM-106
SCRUM-107
SCRUM-108
SCRUM-109
SCRUM-110
SCRUM-111
SCRUM-112
SCRUM-113
SCRUM-114
SCRUM-115
SCRUM-116
SCRUM-117
SCRUM-118
SCRUM-119
SCRUM-120
SCRUM-121
SCRUM-122
SCRUM-123
SCRUM-124
SCRUM-125
SCRUM-126