## Start Here
CS-57 - Contribution Tracker
Human-AI Data Annotation, Provenance & Dataset Evaluation Platform ¦ Group CS-57 ¦ Client: Hunter Xu
The one rule
After your pull request is merged into main, add ONE row to the 'Contribution Log' tab. That is the whole process. Every other tab fills itself in from those rows.
What each tab is for
Contribution Log | The only tab you type into. One row per merged PR. Cream headers = you fill in; grey headers = filled in automatically, do not type in them.
Dashboard | Automatic. Who merged what, per week and in total; review health; the split across frontend / backend / AI.
Jira Statistics | Who owns which bundle, how much of the committed scope is done, workload per person, and every issue on the board matched to the story it serves. Fill in the nine Owner cells once; the rest is a snapshot of docs/Jira.csv plus live PR counts.
Client Report | Set a date range at the top and this becomes the numbers block for the Status Checking form and the weekly client meeting.
Lists | Reference data behind the dropdowns and the automatic columns. Only edit the Week 1 Monday date, and only once.
When you finish a story
Work through this before you ask for a review. If you cannot tick items 1 and 2, the story is not finished - which is fine, but log the PR with 'Story complete? = No'.
1. Open the story in user-stories.html and re-read its acceptance criteria - every numbered criterion, not the one you remember. This is what 'done' means for that story.
2. The checks pass: npm run typecheck and the test suite run clean in whatever you touched (story A2).
3. There is a test covering the behaviour you changed, not only the code you wrote.
4. Anything a teammate could not guess is written down - a change note, and a decision record if you chose between real alternatives.
5. Open the PR with the story ID in the title, e.g. 'C2 - task queue progress'.
6. Request review from someone who did not write the code (story A1), and move the SCRUM ticket to In Review.
7. Once it is merged: move the SCRUM ticket to Done, then add your row to the Contribution Log.
8. Set 'Story complete? = Yes' only if every acceptance criterion is now met. If it closed a catalogued defect, put the issue number in 'Defects closed'.
How to log a merged PR
1. Open 'Contribution Log' and go to the first empty row.
2. Date merged - the date the PR landed on main. The Week column fills itself in from this.
3. Member is you. Reviewed by is the teammate who approved the PR. They must be different people (story A1 - no change reaches main without a second person's review); the sheet turns the row red if they are not.
4. Story ID - pick the backlog story the work serves (A1 ... K4). The story title, epic and priority appear automatically.
5. What changed - one sentence a non-engineer can understand. This sentence is what gets read out to the client, so write it for the client, not for the team.
6. Story complete? - answer 'Yes' only when nothing further is needed for that story. This is what drives every progress number in the workbook.
What a good row looks like
| Date merged | Member | Reviewed by | Work type | Story ID | What changed (plain English, for the client) | Story complete?
| 2026-09-08 | Hanchen Wang | Michael Max | Feature | C2 | A task with 1,000 items now runs in the background and shows a live progress bar, instead of freezing the page. | No - more work to come
| 2026-09-09 | Yi Geng | Dishank Aswal | Defect fix | C3 | When the AI is unavailable the item is now marked 'AI failed' instead of being filled with an invented bounding box. | Yes - story complete
| 2026-09-10 | Parth | Tok Tin Chung | Client / PM / Report | K2 | Wrote up the Week 6 status report and the client's decision on dispute routing. | N/A - not story work
Note what the summaries do not say: no file names, no function names, no ticket jargon. Write the sentence the client would understand if it were read out loud.
Ground rules
- One row per merged PR - not per commit, and not per day of work.
- Log it the same day it merges. A log reconstructed from memory in Week 12 is worth very little to anyone, including you.
- Never delete or reorder someone else's row. If a row is wrong, correct that row.
- Do not insert, delete or reorder columns. The other tabs read this one by column position and will break.
- Work that is not a PR still counts - client meetings, the report, the proposal, research spikes. Log it with work type 'Client / PM / Report' or 'Spike / Research' and leave the PR number blank.
- If one PR serves two stories, log the row against the main story and name the second one in Notes.

## Contribution Log
Date | Week | Member | Reviewed by | Review OK? | SCRUM ticket | PR # | PR link | Work type | Area / repo | Story ID | Story title | Epic | Pri | Defects closed | What changed (plain English, for the client) | Story complete? | Notes / evidence
2026-08-28 | W4 | Yi Geng | Yi Geng | SELF-REVIEW |  | 1 | https://github.com/USYD-CS-Capstone/hej/pull/1 | Refactor | Other | - | (not tied to a backlog story) |  |  |  | Copy the branch name 'week13' (previous team's latest progress) to the main branch | N/A - not story work
2026-09-07 | W6 | Hanchen Wang | Jingwei Lin | OK | SCRUM-82 | 2 | https://github.com/USYD-CS-Capstone/hej/pull/2 | DevOps / CI | CI / tooling | A2 | I can trust that a fix in one place hasn't broken another | A | P0 | 12,13,25,26 | Enable existing testing scripts, so changes can be verified before merging again. | Yes - story complete
2026-09-07 | W6 | Jingwei Lin | Hanchen Wang | OK | SCRUM-44 | 4 | https://github.com/USYD-CS-Capstone/hej/pull/4 | Feature | hej-api (backend) | G1 | My role determines what I can do | G | P0 | 7 | Users now can only perform actions that the role allowed them to do. | Yes - story complete
2026-09-12 | W6 | Jingwei Lin | Hanchen Wang | OK | SCRUM-29 | 6 | https://github.com/USYD-CS-Capstone/hej/pull/6 | Defect fix | hej-api (backend) | D2 | Approval history can't be rewritten behind my back | D | P0 | 8 | Retires the legacy review mutation endpoints that allowed approval history to be changed or deleted without updating the corresponding task-item state. | Yes - story complete
2026-09-12 | W6 | Michael Max | Yi Geng | OK | SCRUM-30 | 7 | https://github.com/USYD-CS-Capstone/hej/pull/7 | Defect fix | hej-web (frontend) | C3 | I'm told when the AI failed instead of being shown a fake answer | C | P0 | 20 | With SCRUM-7; ... | Yes - story complete
2026-09-12 | W6 | Michael Max | Yi Geng | OK | SCRUM-6 | 8 | https://github.com/USYD-CS-Capstone/hej/pull/8 | Feature | labeling_ai_assistnat_mvp (AI) | C1 | The AI assistant can be swapped without disrupting my work | C | P1 | - |  | No - more work to come
2026-09-12 | W6 | Dishank Aswal | Jingwei Lin | OK | SCRUM-22 | 9 | https://github.com/USYD-CS-Capstone/hej/pull/9 | Defect fix | hej-api (backend) | G4 | The platform refuses states that can't exist | G | P1 | 10 | Fixed task status validation and updated the allowed final statuses. | Yes - story complete
2026-09-12 | W6 | Dishank Aswal | Jingwei Lin | OK | SCRUM-23 | 9 | https://github.com/USYD-CS-Capstone/hej/pull/9 | Refactor | hej-api (backend) | B5 | Loading a dataset either works or leaves nothing behind | B | P0 | 29 | Preserved task lifecycle conflict responses as HTTP 409 instead of returning 500 errors. | Yes - story complete
2026-09-12 | W6 | Michael Max | Yi Geng | OK | SCRUM-81 | 10 | https://github.com/USYD-CS-Capstone/hej/pull/10 | Defect fix | hej-api (backend) | A3 | I can get a working copy of the platform running by myself | A | P0 | 23, 24 | With SCRUM-84; ... | No - more work to come
2026-09-12 | W6 | Kanishka Kathait | Jingwei Lin | OK | SCRUM-34 | 11 | https://github.com/USYD-CS-Capstone/hej/pull/11 | Defect fix | hej-api (backend) | B5 | Loading a dataset either works or leaves nothing behind | B | P0 | 16 | Made dataset registration transactional to prevent partial data when AI fails. Added success and rollback tests. | No - more work to come
2026-09-12 | W6 | Hanchen Wang | Yi Geng | OK | SCRUM-25 | 13 | https://github.com/USYD-CS-Capstone/hej/pull/13 | Defect fix | hej-web (frontend) | D6 | My unfinished work is mine | D | P0 | 6 | Enfored draft ownership (1 item - 1 annotator) unfinished draft belongs to its author, otherwise read-only. | Yes - story complete
2026-09-13 | W6 | Jingwei Lin | Michael Max | OK | SCRUM-21 | 14 | https://github.com/USYD-CS-Capstone/hej/pull/14 | Defect fix | hej-api (backend) | G3 | My work stays inside my project | G | P0 | 9 | Enforce project boundaries on task writes | Yes - story complete
2026-09-14 | W7 | Tim Chung | Jingwei Lin | OK | SCRUM-8 | 16 | https://github.com/USYD-CS-Capstone/hej/pull/16 | Feature | hej-api (backend) | G5 | I can actually invite someone into my organisation | G | P0 | 17, 18 | Backend only: registered users can be invited to an organisation and accept invitations successfully. | N/A - not story work
2026-09-14 | W7 | Parth | Dishank Aswal | OK | SCRUM-35 | 17 | https://github.com/USYD-CS-Capstone/hej/pull/17 | Defect fix | hej-web (frontend) | E2 | I can send an item back to the annotator | E | P0 | 15 | User can send an item back to the annotator | Yes - story complete
2026-09-14 | W7 | Parth | Dishank Aswal | OK | SCRUM-31 | 17 | https://github.com/USYD-CS-Capstone/hej/pull/17 | Feature | hej-api (backend) | C5 | I can record why I decided, not just what I decided | C | P1 | - | I can record why I decided, not just what I decided | Yes - story complete
2026-09-14 | W7 | Parth | Dishank Aswal | OK |  | 17 | https://github.com/USYD-CS-Capstone/hej/pull/17 | Feature | CI / tooling | - | (not tied to a backlog story) |  |  | - | Dockerize the application | N/A - not story work
2026-09-14 | W7 | Michael Max | Yi Geng | OK | SCRUM-81 | 18 | https://github.com/USYD-CS-Capstone/hej/pull/18 | Defect fix | hej-api (backend) | A3 | I can get a working copy of the platform running by myself | A | P0 | 23, 24 |  | No - more work to come
2026-09-16 | W7 | Hanchen Wang | Dishank Aswal | OK | SCRUM-28 | 19 | https://github.com/USYD-CS-Capstone/hej/pull/19 | Defect fix | hej-api (backend) | D5 | Finalised means finalised | D | P0 | 2 | A finalised task item will not be mistakenly overwritten. | No - more work to come
2026-09-17 | W7 | Michael Max | Hanchen Wang | OK | SCRUM-2 | 20 | https://github.com/USYD-CS-Capstone/hej/pull/20 | Documentation | Docs / report | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Two proposal design docs for story C2 | No - more work to come
2026-09-17 | W7 | Michael Max | Hanchen Wang | OK | SCRUM-1 | 21 | https://github.com/USYD-CS-Capstone/hej/pull/21 | Feature | Database / schema | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Adds the two tables designed in #20: ai_batch_jobs and ai_item_jobs | No - more work to come
2026-09-18 | W7 | Michael Max | Hanchen Wang | OK | SCRUM-2 | 22 | https://github.com/USYD-CS-Capstone/hej/pull/22 | Feature | hej-api (backend) | C2 | A large batch of items gets AI-annotated reliably | C | P0 | - | Moves the AI model call out of the dataset-registration request and into a worker process | No - more work to come
2026-09-19 | W7 | Hanchen Wang | Kanishka Kathait | OK | SCRUM-26 | 23 | https://github.com/USYD-CS-Capstone/hej/pull/23 | Defect fix | hej-api (backend) | D5 | Finalised means finalised | D | P0 | 11 | Make draft submission atomic; a transaction is all or nothing. | No - more work to come
2026-09-20 | W7 | Parth | Hanchen Wang | OK | SCRUM-94 | 24 | https://github.com/USYD-CS-Capstone/hej/pull/24 | DevOps / CI | Database / schema | C2 | Infrastructure: run on PostgreSQL while keeping SQLite working | A | P0 | - | PostgreSQL is now the default database for native and Docker development. SQLite can still be selected explicitly through DATABASE_URL | No - more work to come | Co-reviewed with Yi Geng.
2026-09-20 | W7 | Jingwei Lin | Parth | OK | SCRUM-20 | 25 | https://github.com/USYD-CS-Capstone/hej/pull/25 | Feature | hej-web (frontend) | B2 | I can decide how carefully my project's work gets reviewed | D | P0 | - | Adds a project-level review and annotation policy layer between organisation defaults and task overrides. | No - more work to come
2026-09-20 | W7 | Dishank Aswal | Kanishka Kathait | OK | SCRUM-43 | 26 | https://github.com/USYD-CS-Capstone/hej/pull/26 | Defect fix | hej-api (backend) | B6 | “Done” means the same thing everywhere I look | B | P1 | 14, 19, 27 | Aligned task completion and export rules so only canonicalized items are treated as final and eligible for export. Centralised the eligibility check and updated the related tests. | Yes - story complete
2026-09-20 | W7 | Yi Geng | Jingwei Lin | OK | SCRUM-6 | 27 | https://github.com/USYD-CS-Capstone/hej/pull/27 | Feature | hej-web (frontend) | C1 | The AI assistant can be swapped without disrupting my work | C | P1 | - | Scrum-6 completed, implement Custom task & label definition & label list upload & schema driven AI output & label editing in project policy page | No - more work to come
2026-09-21 | W7 | Tim Chung |  |  | SCRUM-20 | 28 | https://github.com/USYD-CS-Capstone/hej/pull/28
2026-09-21 | W8 | Michael Max |  |  | SCRUM-46 | 29 | https://github.com/USYD-CS-Capstone/hej/pull/29 | Feature
2026-09-21 | W8 | Michael Max |  |  | SCRUM-3 | 30 | https://github.com/USYD-CS-Capstone/hej/pull/30 | Feature
2026-09-21 | W7 | Yi Geng

## Dashboard
Dashboard
Everything here is calculated from the Contribution Log. Nothing on this tab needs to be typed.
PRS MERGED |  |  | STORIES TOUCHED |  |  | STORIES COMPLETE |  |  | SELF-REVIEWS
30 |  |  | 17 |  |  | 11 |  |  | 1
Contribution by member
Member | PRs merged | PRs reviewed | Features | Defect fixes | Tests / docs | Stories completed | First merge | Last merge | Share of PRs
Michael Max | 9 | 1 | 5 | 3 | 1 | 1 | 2026-09-12 | 2026-09-21 | 30%
Parth | 4 | 1 | 2 | 1 | 0 | 2 | 2026-09-14 | 2026-09-20 | 13.33%
Jingwei Lin | 4 | 6 | 2 | 2 | 0 | 3 | 2026-09-07 | 2026-09-20 | 13.33%
Hanchen Wang | 4 | 6 | 0 | 3 | 0 | 2 | 2026-09-07 | 2026-09-19 | 13.33%
Yi Geng | 3 | 6 | 1 | 0 | 0 | 0 | 2026-08-28 | 2026-09-21 | 10%
Dishank Aswal | 3 | 4 | 0 | 2 | 0 | 3 | 2026-09-12 | 2026-09-20 | 10%
Kanishka Kathait | 1 | 2 | 0 | 1 | 0 | 0 | 2026-09-12 | 2026-09-12 | 3.333%
Tim Chung | 2 | 0 | 1 | 0 | 0 | 0 | 2026-09-14 | 2026-09-21 | 6.667%
TOTAL | 30 | 26 | 11 | 12 | 1 | 11
TOTAL counts distinct stories, so it can be lower than the column above if two people finished the same story.
PRs merged per week | [5 empty] | Weeks are calculated from the date merged. Blank weeks simply have nothing logged yet.
Week | Michael Max | Parth | Jingwei Lin | Hanchen Wang | Yi Geng | Dishank Aswal | Kanishka Kathait | Tim Chung | Total
W1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
W5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W6 | 3 | 0 | 3 | 2 | 0 | 2 | 1 | 0 | 11
W7 | 4 | 4 | 1 | 2 | 2 | 1 | 0 | 2 | 16
W8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
W12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Where the work went | [5 empty] | Review health
Area / repo | PRs |  | Work type | PRs
hej-web (frontend) | 5 |  | Feature | 11 |  | PRs with a named reviewer | 25
hej-api (backend) | 14 |  | Defect fix | 12 |  | PRs reviewed by their own author | 1
packages/ui | 0 |  | Refactor | 2 |  | Rows with no reviewer recorded | 4
labeling_ai_assistnat_mvp (AI) | 1 |  | Tests | 0 |  | Rows with no story linked | 4
Database / schema | 2 |  | Documentation | 1 |  | Rows missing a plain-English summary | 6
CI / tooling | 2 |  | Spike / Research | 0
Docs / report | 1 |  | DevOps / CI | 2
Other | 1 |  | Client / PM / Report | 0

## Jira Statistics
Jira Statistics
The CS-57 board, matched to the 59 committed backlog stories. Status and assignees are a snapshot of docs/Jira.csv; PR counts are live from the Contribution Log. Only the nine Owner cells are typed.
WORK ITEMS |  | IN PROGRESS |  | IN REVIEW |  | DONE |  | IN SPRINT W7 |  | UNASSIGNED
76 |  | 1 |  | 3 |  | 31 |  | 18 |  | 36
Work bundles | [5 empty] | Fill in the nine Owner cells once. This is the only typing on this tab.
# | Work bundle | What it covers |  | Stories | To do | Doing | Done | PRs
1 | AI task queue | Task queue with progress bar; completed / failed / retry |  | 1 | 0 | 1 | 0 | 4
2 | AI provider & failures | Annotation failure and the fake bounding-box fallback; integrate labeling_ai_assistnat_mvp |  | 1 | 0 | 0 | 1 | 1
3 | Project setup & status UI | Project / policy / task update, dataset upload, status page |  | 7 | 4 | 2 | 1 | 2
4 | Task & item backend | Illegal item status, cross-project writes, non-transactional task registration, missing transition out of draft, task-item routes and services |  | 4 | 1 | 0 | 3 | 4
5 | Annotation page & judgement | Annotation page with judgement feedback or justification |  | 6 | 3 | 2 | 1 | 2
6 | Draft ownership & verdict | Finalised annotation overwrite, draft ownership, judgement verdict and feedback |  | 3 | 1 | 0 | 2 | 3
7 | Review, permissions & dispute | Reviewer correction, avoid self-review, review action, permission and dispute |  | 8 | 6 | 2 | 0 | 2
8 | Audit & history | Audit and history |  | 4 | 3 | 0 | 1 | 1
9 | Release & export | Release and export |  | 5 | 4 | 0 | 1 | 0
- | Unallocated | Not in the allocation document. Assign these before they become a surprise. |  | 20 | 10 | 0 | 4 | 5
Committed scope | [5 empty] | Done counts what the board says is done. A story with no ticket cannot be done. | By epic
Priority | Stories | Done | Doing | On board | % done |  | Epic | Stories | Done
P0 - committed core | 35 | 10 | 5 | 32 | 28.57% |  | A - Trustworthy Foundations | 5 | 3
P1 | 20 | 4 | 1 | 17 | 20% |  | B - Setting Up Work | 6 | 2
P2 - nice to have | 4 | 0 | 1 | 4 | 0% |  | C - AI-Assisted First Pass | 5 | 2
All stories | 59 | 14 | 7 | 53 | 23.73% |  | D - Review & Cross-Validation | 8 | 2
[7 empty] | E - Disagreement & Dispute | 6 | 1
[7 empty] | F - Provenance & History | 5 | 0
[7 empty] | G - Roles, Permissions & Organisations | 5 | 3
[7 empty] | H - Release & Export | 6 | 1
[7 empty] | I - Evaluation | 5 | 0
[7 empty] | J - Organisations & Dashboard | 4 | 0
[7 empty] | K - Evidence & Handover | 4 | 0
Waiting for a ticket | [5 empty] | Committed stories with nothing on the board. Nobody is working on these, because there is nothing to pick up.
None | Every committed story that is not dropped has at least one ticket on the board.
Dropped | 6 stories the team dropped, so no ticket is expected: A1 A5 K1 K2 K3 K4
Workload by person | [5 empty] | Issues assigned on the board, beside PRs actually logged. Both count the same eight people.
Member | Assigned | To do | Doing | In review | Done | In sprint | Bundles touched | PRs logged | Reviews
Michael Max | 7 | 1 | 0 | 2 | 4 | 2 | AI task queue, AI provider & failures | 9 | 1
Parth | 7 | 4 | 0 | 0 | 3 | 1 | Annotation page & judgement, Review, permissions & dispute, AI task queue | 4 | 1
Jingwei Lin | 6 | 2 | 0 | 0 | 4 | 1 | Project setup & status UI, Task & item backend, Draft ownership & verdict, Review, permissions & dispute, Unallocated | 4 | 6
Hanchen Wang | 6 | 2 | 0 | 0 | 4 | 2 | Draft ownership & verdict, Unallocated, Review, permissions & dispute | 4 | 6
Yi Geng | 4 | 1 | 0 | 0 | 3 | 1 | Unallocated, Audit & history | 3 | 6
Dishank Aswal | 4 | 1 | 0 | 0 | 3 | 1 | Task & item backend, Audit & history, Release & export | 3 | 4
Kanishka Kathait | 3 | 1 | 1 | 0 | 1 | 1 | Task & item backend, Annotation page & judgement | 1 | 2
Tim Chung | 3 | 1 | 0 | 1 | 1 | 2 | Project setup & status UI, Unallocated | 2 | 0
Nobody assigned | 36 | 36 of 76 issues on the board have no owner - including every issue in Evaluation Harness and Casebook.
Every issue on the board
Issue | Type | Status | Assignee | Sprint | Jira epic | Summary | Backlog story | Matched from | PRs
SCRUM-1 | Task | Done | Michael Max | W7 Lock down review data | AI Annotation Pipeline | Task queue: Create AI batch job and per-item job status models | C2 | description | 1
SCRUM-2 | Task | Done | Michael Max | W7 Lock down review data | AI Annotation Pipeline | Task queue: Execute task annotation asynchronously through a worker | C2 | description | 2
SCRUM-3 | Task | In Review | Michael Max | W8 Route work, record decision | AI Annotation Pipeline | Task queue: Retry failed items and preserve permanent failures | C2 | description | 1
SCRUM-5 | Task | To Do | Michael Max | Mid-semester Break | AI Annotation Pipeline | Task queue: Display batch progress and per-item job status | C2 | description
SCRUM-6 | Task | Done | Yi Geng | W7 Lock down review data | Annotation & Human Judgement | AI-Provider: Integrate labeling_ai_assistnat_mvp as an AI provider | C1 | description | 2
SCRUM-7 | Task | Done | Michael Max | W6 Governance & data-integrity | Annotation & Human Judgement | AI-Provider: Stop generating fake annotations when the AI provider fails | C3 | description | 0
SCRUM-8 | Task | Done | Tim Chung | W7 Lock down review data | Organisation Management | Organisation management: Invitation & acceptance | G5 | description | 1
SCRUM-20 | Task | Done | Jingwei Lin | W7 Lock down review data | Project, Policy & Task Lifecycle | Project & Policy: Configure project review and annotation policies | B2 | description | 2
SCRUM-21 | Task | Done | Jingwei Lin | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Prevent cross-project task and task-item writes | G3 | description | 1
SCRUM-22 | Task | Done | Dishank Aswal | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Validate task-item status before database commit | G4 | description | 1
SCRUM-23 | Task | Done | Dishank Aswal | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Preserve lifecycle conflict responses as HTTP 409 | B5 | description | 1
SCRUM-24 | Task | To Do | Dishank Aswal | W8 Route work, record decision | Project, Policy & Task Lifecycle | Task Lifecycle: Implement valid task lifecycle transitions | B4 | description | 0
SCRUM-25 | Task | Done | Hanchen Wang | W6 Governance & data-integrity | Annotation & Human Judgement | Annotation: Enforce draft ownership | D6 | description | 1
SCRUM-26 | Task | Done | Hanchen Wang | W7 Lock down review data | Annotation & Human Judgement | Annotation: Make draft submission and annotation creation atomic | D5 | description | 1
SCRUM-27 | Task | To Do | Jingwei Lin | W8 Route work, record decision | Review, Dispute & Adjudication | Review / Annotation: Reviewer should be able to select the correct submitted annotation | D4 | description | 0
SCRUM-28 | Task | Done | Hanchen Wang | W7 Lock down review data | Annotation & Human Judgement | Annotation: Preventing finalized annotations from being overwritten | D5 | description | 1
SCRUM-29 | Task | Done | Jingwei Lin | W6 Governance & data-integrity | Review, Dispute & Adjudication | Review: Retire or restrict legacy review mutation endpoints | D2 | description | 1
SCRUM-30 | Task | Done | Michael Max | W6 Governance & data-integrity | Annotation & Human Judgement | AI-Provider: Store & Display AI suggestions, failures and unavailable states | C3 | description | 1
SCRUM-31 | Task | Done | Parth | W6 Governance & data-integrity | Review, Dispute & Adjudication | Review: Record verdict, feedback & justification | C5 | description | 1
SCRUM-32 | Task | To Do |  | W9 | Review, Dispute & Adjudication | Review: Persist reviewer corrections as structured data | D3 | description | 0
SCRUM-34 | Task | Done | Kanishka Kathait | W6 Governance & data-integrity | Project, Policy & Task Lifecycle | Task Lifecycle: Make dataset registration transactional | B5 | description | 1
SCRUM-35 | Task | Done | Parth | W6 Governance & data-integrity | Review, Dispute & Adjudication | Dispute / Annotation: Implement "Dispute & send back to annotator" | E2 | description | 1
SCRUM-37 | Task | To Do |  |  | Provenance & Audit History | Provenance: Guarantee one canonical answer per task item | H4 | description | 0
SCRUM-38 | Task | To Do |  |  | Provenance & Audit History | Provenance: Preserve AI, annotator, reviewer and adjudicator outputs separately | F3 | description | 0
SCRUM-40 | Task | To Do |  |  | Provenance & Audit History | Provenance: Record correct audit actor types | F4 | description | 0
SCRUM-41 | Task | To Do |  |  | Provenance & Audit History | Provenance: Remove duplicate escalation audit changes | F4 | description | 0
SCRUM-43 | Task | Done | Dishank Aswal | W7 Lock down review data | Dataset Release & Export | Release & Export: Align task completion and export readiness | B6, H5 | description | 1
SCRUM-44 | Task | Done | Jingwei Lin | W6 Governance & data-integrity | Organisation Management | Organisation Management: Users can only perform actions that are permitted by their roles. | G1 | backlog CSV | 1
SCRUM-45 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Project lifecycle: Update and archive a project | J4 | description | 0
SCRUM-46 | Task | In Review | Michael Max | W8 Route work, record decision | AI Annotation Pipeline | Task queue: Trigger an AI run and route completed items to review | C2 | description | 1
SCRUM-47 | Task | Done |  |  | Annotation & Human Judgement | Annotation: Connect the existing text annotation page to live APIs |  |  | 0
SCRUM-48 | Task | In Progress | Kanishka Kathait | W7 Lock down review data | Review, Dispute & Adjudication | Work queues: role-checked queues, annotator count and submission limit (API) | D8 | description | 0
SCRUM-49 | Task | To Do |  |  | Review, Dispute & Adjudication | Review: Execute accept, adjust, reject and dispute transitions | C5, D3, E1 | description | 0
SCRUM-50 | Task | To Do | Jingwei Lin | W8 Route work, record decision | Project, Policy & Task Lifecycle | Policy: Resolve project policy into executable task rules | B2, G2 | description | 0
SCRUM-51 | Task | To Do | Parth | W8 Route work, record decision | Review, Dispute & Adjudication | Review: Independent second reviewer | D7, E1 | description | 0
SCRUM-52 | Task | To Do | Parth | W9 | Review, Dispute & Adjudication | Dispute: Adjudicator queue and authorization | D8, E3, E6, G1 | description | 0
SCRUM-53 | Task | To Do |  |  | Provenance & Audit History | Provenance: Version guidelines, sources and review policies | F2 | description | 0
SCRUM-54 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Define the AnnotationAssistant interface | C1 | parent ticket | 0
SCRUM-55 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Replace the Gemini call with an OpenAI-compatible client | C1 | parent ticket | 0
SCRUM-56 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Port the MVP's four text tasks behind the interface | C1 | parent ticket | 0
SCRUM-68 | Task | To Do |  | Mid-semester Break | Evaluation Harness and Casebook | Evaluation1: Scenario harness that drives the workflow end to end | I1 | description | 0
SCRUM-69 | Task | To Do |  | Mid-semester Break | Evaluation Harness and Casebook | Evaluation2: Repeatable runs and regression reporting | I1 | description | 0
SCRUM-70 | Task | To Do |  | Mid-semester Break | Evaluation Harness and Casebook | Evaluation3: Casebook structure and the adversarial categories | I2 | description | 0
SCRUM-71 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation4: Grow the casebook to 40–60 cases | I2 | description | 0
SCRUM-72 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation5: Reviewer agreement and AI suggestion quality | I3 | description | 0
SCRUM-73 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation6: Measure AI influence on human judgement, with blind-then-reveal | I4 | description | 0
SCRUM-74 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation7: Integrity checks on provenance, roles and releases | I5 | description | 0
SCRUM-75 | Task | To Do |  |  | Evaluation Harness and Casebook | Evaluation8: Findings record including negative results | I5 | backlog CSV | 0
SCRUM-81 | Task | Done | Yi Geng | W6 Governance & data-integrity | Trustworthy Foundations | Schema: Fix db setup issues | A3 | backlog CSV | 2
SCRUM-82 | Task | Done | Hanchen Wang | W6 Governance & data-integrity | Trustworthy Foundations | Schema: Restore existing testcases | A2 | backlog CSV | 1
SCRUM-84 | Task | Done | Yi Geng | W6 Governance & data-integrity | Trustworthy Foundations | Schema: Replace hardcoded credentials | A4 | backlog CSV | 0
SCRUM-85 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Task lifecycle: Create annotation and judgement tasks with a result shape | B3 | description | 0
SCRUM-86 | Task | To Do | Parth | W8 Route work, record decision | Review, Dispute & Adjudication | Review: Prevent self-review of own annotations | D1 | description | 0
SCRUM-87 | Task | To Do |  |  | Annotation & Human Judgement | AI assist: Human-only and AI-first task modes | C4 | description | 0
SCRUM-88 | Task | To Do |  |  | Organisation Management | Organisation Management: Stable organisation identifier and URL | J1 | description | 0
SCRUM-89 | Task | To Do | Tim Chung | W8 Route work, record decision | Project, Policy & Task Lifecycle | Project: Overview of status and progress | J2 | description
SCRUM-90 | Task | In Review | Tim Chung | W7 Lock down review data | Organisation Management | Organisation Management: Invite, remove and role-manage members | J3 | description | 0
SCRUM-91 | Task | To Do |  |  | Project, Policy & Task Lifecycle | Project lifecycle: Create a project scoped to an organisation | B1 | description | 0
SCRUM-92 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Update the annotation editing page to ensure that the output results of MVP can be compatible with the existing interface of Hej. | C1 | parent ticket | 0
SCRUM-93 | Task | To Do | Kanishka Kathait | W8 Route work, record decision | Review, Dispute & Adjudication | Work queues: available-work list, progress and submission limit (WEB) | D8 | description | 0
SCRUM-94 | Task | Done | Parth | W7 Lock down review data | Trustworthy Foundations | Infrastructure: run on PostgreSQL while keeping SQLite working | C2 | description | 1
SCRUM-95 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Add definition settings to labels field | C1 | parent ticket | 0
SCRUM-96 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | Enable label list file upload | C1 | parent ticket | 0
SCRUM-97 | Subtask | Done |  | W7 Lock down review data | Annotation & Human Judgement | enable custom task with user-defined instructions, output-type and schema | C1 | parent ticket | 0
SCRUM-98 | Task | To Do | Yi Geng | W8 Route work, record decision | Provenance & Audit History | Provenance: Record the production history of every label | F1 | description | 0
SCRUM-99 | Task | To Do | Hanchen Wang | W8 Route work, record decision | Review, Dispute & Adjudication | Dispute: Record an expert adjudication as its own decision | E3 | description | 0
SCRUM-100 | Task | To Do | Hanchen Wang | W8 Route work, record decision | Review, Dispute & Adjudication | Dispute: Keep the disagreement after the dispute is resolved | E4 | description | 0
SCRUM-101 | Task | To Do |  | W9 | Review, Dispute & Adjudication | Dispute: Detect reviewer disagreement automatically | E1 | description | 0
SCRUM-102 | Task | To Do |  | W9 | Dataset Release & Export | Release: Create an immutable release artefact | H1 | description | 0
SCRUM-103 | Task | To Do |  | W10 | Review, Dispute & Adjudication | Dispute: Connect the dispute and arbitration screens | E6 | description | 0
SCRUM-104 | Task | To Do |  | W10 | Dataset Release & Export | Release: Produce a manifest for every release | H2 | description | 0
SCRUM-105 | Task | To Do |  | W10 | Dataset Release & Export | Release: Refuse a release that fails its pre-release checks | H3 | description | 0
SCRUM-106 | Task | To Do |  | W11 | Provenance & Audit History | Provenance: Show an item's whole timeline on one screen | F5 | description | 0
SCRUM-107 | Task | To Do |  | W11 | Review, Dispute & Adjudication | Dispute: Make the escalation posture configurable and enforced | E5 | description | 0
SCRUM-108 | Task | To Do |  | W11 | Dataset Release & Export | Release: Show real releases, policy and history on the project screens | H6 | description | 0
SCRUM-109 | Task | To Do | Parth | W8 Route work, record decision | Review, Dispute & Adjudication | Review: Review actions always move item status, and state cannot diverge from history | D2 | description | 0

## Client Report
Client Report
Set the two dates below. Everything else recalculates for that period - ready to paste into the Status Checking form or the weekly client meeting.
Reporting period starts | 2026-09-16 | <- type the two dates here
Reporting period ends | 2026-09-23
This period at a glance |  |  | Delivery by epic, this period
PRs merged | 13 |  | Epic | PRs | Stories done
Members who merged | 7 |  | A - Trustworthy Foundations | 1 | 0
Stories completed | 1 |  | B - Setting Up Work | 1 | 1
Defect-fix PRs | 3 |  | C - AI-Assisted First Pass | 4 | 0
Feature PRs | 6 |  | D - Review & Cross-Validation | 3 | 0
PRs reviewed by a second person | 9 |  | E - Disagreement & Dispute | 0 | 0
|  |  | F - Provenance & History | 0 | 0
|  |  | G - Roles, Permissions & Organisations | 0 | 0
|  |  | H - Release & Export | 0 | 0
Individual contribution, this period |  |  | I - Evaluation | 0 | 0
Member | PRs | Reviews given | Stories completed
Michael Max | 5 | 0 | 0
Parth | 1 | 1 | 0
Jingwei Lin | 1 | 1 | 0
Hanchen Wang | 2 | 4 | 0
Yi Geng | 2 | 0 | 0
Dishank Aswal | 1 | 1 | 1
Kanishka Kathait | 0 | 2 | 0
Tim Chung | 1 | 0 | 0

## Lists
Members | Week 1 Monday | Work type | Area / repo | Story complete? | Epic | Story ID | Epic | Priority | Role | Story title | SCRUM ticket(s) | Week | Starts | Ends | Work bundle | Jira status | SCRUM ticket
Michael Max | 2026-08-03 | Feature | hej-web (frontend) | Yes - story complete | A | - |  |  |  | (not tied to a backlog story) |  | W1 | 2026-08-03 | 2026-08-09 |  |  | SCRUM-1
Parth | Check this date once, then leave it alone. | Defect fix | hej-api (backend) | No - more work to come | B | A1 | A | P0 | Lead | Changes are reviewed before they reach the platform |  | W2 | 2026-08-10 | 2026-08-16 | Unallocated | Dropped | SCRUM-2
Jingwei Lin | Every Week number is counted from here. | Refactor | packages/ui | N/A - not story work | C | A2 | A | P0 | SC | I can trust that a fix in one place hasn't broken another | SCRUM-82 | W3 | 2026-08-17 | 2026-08-23 | Unallocated | Done | SCRUM-3
Hanchen Wang | To check it: look at the week calendar in columns T-V. | Tests | labeling_ai_assistnat_mvp (AI) |  | D | A3 | A | P0 | SC | I can get a working copy of the platform running by myself | SCRUM-81 | W4 | 2026-08-24 | 2026-08-30 | Unallocated | Done | SCRUM-5
Yi Geng | W6 should read Mon 7 Sep 2026, and W12 should be the last week. The mid-semester break (28 Sep) is its own week, Break. | Documentation | Database / schema |  | E | A4 | A | P0 | SC | Platform credentials aren't sitting in shared code | SCRUM-84 | W5 | 2026-08-31 | 2026-09-06 | Unallocated | Done | SCRUM-6
Dishank Aswal |  | Spike / Research | CI / tooling |  | F | A5 | A | P0 | SC | A status means the same thing wherever I see it |  | W6 | 2026-09-07 | 2026-09-13 | Unallocated | Dropped | SCRUM-7
Kanishka Kathait |  | DevOps / CI | Docs / report |  | G | B1 | B | P0 | BE/FE | I can create a project to hold related work | SCRUM-91 | W7 | 2026-09-14 | 2026-09-23 | Project setup & status UI | To Do | SCRUM-8
Tim Chung |  | Client / PM / Report | Other |  | H | B2 | B | P0 | BE | I can decide how carefully my project's work gets reviewed | SCRUM-20, SCRUM-50 | W8 | 2026-09-24 | 2026-09-30 | Project setup & status UI | In progress | SCRUM-20
[5 empty] | I | B3 | B | P0 | BE/FE | I can create a task for a specific piece of work | SCRUM-85 | Break | 2026-10-01 | 2026-10-07 | Project setup & status UI | To Do | SCRUM-21
[5 empty] | J | B4 | B | P0 | BE | My task moves through real states, not just “draft” | SCRUM-24 | W9 | 2026-10-08 | 2026-10-14 | Task & item backend | To Do | SCRUM-22
[5 empty] | K | B5 | B | P0 | BE | Loading a dataset either works or leaves nothing behind | SCRUM-23, SCRUM-34 | W10 | 2026-10-15 | 2026-10-21 | Task & item backend | Done | SCRUM-23
[6 empty] | B6 | B | P1 | BE | “Done” means the same thing everywhere I look | SCRUM-43 | W11 | 2026-10-22 | 2026-10-28 | Audit & history | Done | SCRUM-24
[6 empty] | C1 | C | P1 | BE | The AI assistant can be swapped without disrupting my work | SCRUM-6 | W12 | 2026-10-29 | 2026-11-01 | Unallocated | Done | SCRUM-25
[6 empty] | C2 | C | P0 | BE | A large batch of items gets AI-annotated reliably | SCRUM-1, SCRUM-2, SCRUM-3, SCRUM-5, SCRUM-46, SCRUM-94 | End |  | 2026-11-01 | AI task queue | In progress | SCRUM-26
[6 empty] | C3 | C | P0 | BE | I'm told when the AI failed instead of being shown a fake answer | SCRUM-7, SCRUM-30 | Project ends at the close of W12. |  |  | AI provider & failures | Done | SCRUM-27
[6 empty] | C4 | C | P1 | BE/FE | I can control whether reviewers see the AI's answer first | SCRUM-87 |  |  |  | Annotation page & judgement | To Do | SCRUM-28
[6 empty] | C5 | C | P1 | BE/FE | I can record why I decided, not just what I decided | SCRUM-31, SCRUM-49 |  |  |  | Annotation page & judgement | In progress | SCRUM-29
[6 empty] | D1 | D | P0 | BE | I can't approve my own work | SCRUM-86 |  |  |  | Review, permissions & dispute | To Do | SCRUM-30
[6 empty] | D2 | D | P0 | BE | Approval history can't be rewritten behind my back | SCRUM-29, SCRUM-109 |  |  |  | Review, permissions & dispute | In progress | SCRUM-31
[6 empty] | D3 | D | P0 | BE | The correction I make is the answer that gets saved | SCRUM-32, SCRUM-49 |  |  |  | Review, permissions & dispute | To Do | SCRUM-32
[6 empty] | D4 | D | P0 | BE | I know I'm reviewing the right person's work | SCRUM-27 |  |  |  | Draft ownership & verdict | To Do | SCRUM-34
[6 empty] | D5 | D | P0 | BE | Finalised means finalised | SCRUM-26, SCRUM-28 |  |  |  | Draft ownership & verdict | Done | SCRUM-35
[6 empty] | D6 | D | P0 | BE | My unfinished work is mine | SCRUM-25 |  |  |  | Draft ownership & verdict | Done | SCRUM-37
[6 empty] | D7 | D | P1 | BE | A defined share of items gets independently double-checked | SCRUM-51 |  |  |  | Annotation page & judgement | To Do | SCRUM-38
[6 empty] | D8 | D | P0 | BE/FE | Work reaches the right person | SCRUM-48, SCRUM-52, SCRUM-93 |  |  |  | Annotation page & judgement | In progress | SCRUM-40
[6 empty] | E1 | E | P0 | BE | Disagreement is noticed without anyone reporting it | SCRUM-49, SCRUM-51, SCRUM-101 |  |  |  | Review, permissions & dispute | To Do | SCRUM-41
[6 empty] | E2 | E | P0 | FE | I can send an item back to the annotator | SCRUM-35 |  |  |  | Annotation page & judgement | Done | SCRUM-43
[6 empty] | E3 | E | P1 | BE | An expert's decision is recorded as its own decision | SCRUM-52, SCRUM-99 |  |  |  | Review, permissions & dispute | To Do | SCRUM-44
[6 empty] | E4 | E | P1 | BE | Resolving a dispute doesn't erase the disagreement | SCRUM-100 |  |  |  | Review, permissions & dispute | To Do | SCRUM-45
[6 empty] | E5 | E | P1 | BE | Escalation matches the assurance my project needs | SCRUM-107 |  |  |  | Review, permissions & dispute | To Do | SCRUM-46
[6 empty] | E6 | E | P0 | FE | The dispute and arbitration screens show my real cases | SCRUM-52, SCRUM-103 |  |  |  | Annotation page & judgement | To Do | SCRUM-47
[6 empty] | F1 | F | P0 | BE | I can ask how any label came to exist | SCRUM-98 |  |  |  | Audit & history | To Do | SCRUM-48
[6 empty] | F2 | F | P1 | BE | Annotations remember which guideline they followed | SCRUM-53 |  |  |  | Unallocated | To Do | SCRUM-49
[6 empty] | F3 | F | P0 | BE | The AI's suggestion, the human's answer and the reviewer's correction stay separate | SCRUM-38 |  |  |  | Audit & history | To Do | SCRUM-50
[6 empty] | F4 | F | P1 | BE | History tells me who really did what | SCRUM-40, SCRUM-41 |  |  |  | Audit & history | To Do | SCRUM-51
[6 empty] | F5 | F | P1 | FE | I can see an item's whole story on one screen | SCRUM-106 |  |  |  | Unallocated | To Do | SCRUM-52
[6 empty] | G1 | G | P0 | BE | My role determines what I can do | SCRUM-44, SCRUM-52 |  |  |  | Review, permissions & dispute | In progress | SCRUM-53
[6 empty] | G2 | G | P1 | BE | My project's governance posture actually governs | SCRUM-50 |  |  |  | Unallocated | To Do | SCRUM-54
[6 empty] | G3 | G | P0 | BE | My work stays inside my project | SCRUM-21 |  |  |  | Task & item backend | Done | SCRUM-55
[6 empty] | G4 | G | P1 | BE/SC | The platform refuses states that can't exist | SCRUM-22 |  |  |  | Task & item backend | Done | SCRUM-56
[6 empty] | G5 | G | P0 | BE | I can actually invite someone into my organisation | SCRUM-8 |  |  |  | Project setup & status UI | Done | SCRUM-68
[6 empty] | H1 | H | P0 | BE | A release is a fixed thing I can point at | SCRUM-102 |  |  |  | Release & export | To Do | SCRUM-69
[6 empty] | H2 | H | P0 | BE | Every release explains what's in it | SCRUM-104 |  |  |  | Release & export | To Do | SCRUM-70
[6 empty] | H3 | H | P0 | BE | A release that shouldn't exist is refused | SCRUM-105 |  |  |  | Release & export | To Do | SCRUM-71
[6 empty] | H4 | H | P0 | BE | Every released item has exactly one authoritative answer | SCRUM-37 |  |  |  | Release & export | To Do | SCRUM-72
[6 empty] | H5 | H | P1 | BE | Export figures agree with the rest of the platform | SCRUM-43 |  |  |  | Release & export | Done | SCRUM-73
[6 empty] | H6 | H | P0 | FE | The export, policy and history screens show real data | SCRUM-108 |  |  |  | Unallocated | To Do | SCRUM-74
[6 empty] | I1 | I | P0 | GOV | I can re-run the whole workflow against known cases | SCRUM-68, SCRUM-69 |  |  |  | Unallocated | To Do | SCRUM-75
[6 empty] | I2 | I | P0 | GOV | The platform is tested against cases designed to break it | SCRUM-70, SCRUM-71 |  |  |  | Unallocated | To Do | SCRUM-81
[6 empty] | I3 | I | P1 | GOV | I can tell whether reviewers actually agree | SCRUM-72 |  |  |  | Unallocated | To Do | SCRUM-82
[6 empty] | I4 | I | P1 | GOV | I can see what AI assistance does to human judgement | SCRUM-73 |  |  |  | Unallocated | To Do | SCRUM-84
[6 empty] | I5 | I | P1 | GOV | I can prove the platform's records hold up | SCRUM-74, SCRUM-75 |  |  |  | Unallocated | To Do | SCRUM-85
[6 empty] | J1 | J | P2 | BE | My organisation has a stable identity | SCRUM-88 |  |  |  | Project setup & status UI | To Do | SCRUM-86
[6 empty] | J2 | J | P2 | FE | I can see how my project is going at a glance | SCRUM-89 |  |  |  | Unallocated | To Do | SCRUM-87
[6 empty] | J3 | J | P2 | BE/FE | I can invite and manage my team | SCRUM-90 |  |  |  | Project setup & status UI | In progress | SCRUM-88
[6 empty] | J4 | J | P2 | BE/FE | I can maintain a project after creating it | SCRUM-45 |  |  |  | Project setup & status UI | To Do | SCRUM-89
[6 empty] | K1 | K | P1 | Lead | A reader can understand the system without us in the room |  |  |  |  | Unallocated | Dropped | SCRUM-90
[6 empty] | K2 | K | P1 | all | Each of us can defend our own design decisions |  |  |  |  | Unallocated | Dropped | SCRUM-91
[6 empty] | K3 | K | P1 | GOV | What didn't work is recorded as carefully as what did |  |  |  |  | Unallocated | Dropped | SCRUM-92
[6 empty] | K4 | K | P0 | Lead | The end-to-end demonstration works when it matters |  |  |  |  | Unallocated | Dropped | SCRUM-93
SCRUM-94
SCRUM-95
SCRUM-96
SCRUM-97
SCRUM-98
SCRUM-99
SCRUM-100
SCRUM-101
SCRUM-102
SCRUM-103
SCRUM-104
SCRUM-105
SCRUM-106
SCRUM-107
SCRUM-108
SCRUM-109